## 1 Project Overview
Field | Value
Project Title | Patient-Specific Cardiac Digital Twin Construction and Gravity-Dependent Multiphysics Simulation Pipeline
Objective | Construct patient-specific cardiac digital twins from the finalized 645-subject harmonized cohort and execute multiphysics simulation under 4 gravitational environments.
Representative Cohort | 10 subjects (5 ACDC, 4 Sunnybrook, 1 CAMUS) - identical to Simulation_Subject_Execution_Workbook.xlsx Sheet 1, for full traceability
Total Planned Simulations | 10 patients x 4 gravity conditions = 40 simulations
Gravity Conditions | Earth (9.80665 m/s^2), Mars (3.71 m/s^2), Moon (1.62 m/s^2), Microgravity (0 m/s^2)
Traceability Keys | Subject_ID, Original_Dataset_ID, Disease_Group, Simulation_ID - carried identically through every sheet in this workbook and into Digital_Twin_Simulation_Results_Workbook.xlsx
Pipeline Phases | 1 Image Loading -> 2 Preprocessing -> 3 Geometry Reconstruction -> 4 Mesh Generation -> 5 Fiber Assignment -> 6 Material Properties -> 7 Electrophysiology -> 8 Boundary Conditions -> 9 Gravity -> 10 COMSOL Setup -> 11 Execution -> 12 Output Export -> 13 Gravity Comparison -> 14 Validation -> 15 Quality Control
Downstream Workbook | Digital_Twin_Simulation_Results_Workbook.xlsx - all 40 simulations' numerical outputs will populate that workbook once Phase 11 (Simulation Execution) is actually run
Current Status | Planning and specification complete. No image has been loaded, no geometry reconstructed, no mesh generated, and no COMSOL simulation executed for any of the 10 subjects in this project.

## 2 Patient Selection
Simulation_ID | Subject_ID | Original_Dataset_ID | Dataset | Disease_Group | Imaging_Modality | Status
SIM-001 | ACDC_patient001 | patient001 | ACDC | DCM (Dilated Cardiomyopathy) | MRI | Proposed
SIM-002 | ACDC_patient021 | patient021 | ACDC | HCM (Hypertrophic Cardiomyopathy) | MRI | Proposed
SIM-003 | ACDC_patient041 | patient041 | ACDC | MINF (Myocardial Infarction) | MRI | Proposed
SIM-004 | ACDC_patient061 | patient061 | ACDC | NOR (Normal) | MRI | Proposed
SIM-005 | ACDC_patient081 | patient081 | ACDC | RV (Abnormal Right Ventricle) | MRI | Proposed
SIM-006 | SUNNYBROOK_SC-N-2 | SC-N-2 | Sunnybrook | N (Normal) | MRI | Proposed
SIM-007 | SUNNYBROOK_SC-HYP-1 | SC-HYP-1 | Sunnybrook | HYP (Hypertrophy) | MRI | Proposed
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | SC-HF-NI-3 | Sunnybrook | HF (Heart Failure without infarction) | MRI | Proposed
SIM-009 | SUNNYBROOK_SC-HF-I-1 | SC-HF-I-1 | Sunnybrook | HF-I (Heart Failure with Infarction) | MRI | Proposed
SIM-010 | CAMUS_patient0001 | patient0001 | CAMUS | Not released in public metadata (cohort-level only) | Echocardiography | Proposed
Identical subject set to Simulation_Subject_Execution_Workbook.xlsx Sheet 1, per the instruction to use representative patients exactly as already documented. Status remains 'Proposed' until the research team makes a final selection decision.

## 3 Image Loading
Simulation_ID | Subject_ID | Filename | Voxel_Spacing_mm | Slice_Thickness_mm | Frame_Indices | Image_Loaded | Orientation_Verified | Spacing_Verified | Coordinate_System_Verified | Slice_Order_Verified
SIM-001 | ACDC_patient001 | training/patient001/patient001_4d.nii.gz | 1.562 x 1.562 | 10 | ED=1 (real); ES per official Info.cfg | No | No | No | No | No
SIM-002 | ACDC_patient021 | training/patient021/patient021_4d.nii.gz | 1.68 x 1.68 | 10 | ED=1 (real); ES per official Info.cfg | No | No | No | No | No
SIM-003 | ACDC_patient041 | training/patient041/patient041_4d.nii.gz | 1.786 x 1.786 | 10 | ED=1 (real); ES per official Info.cfg | No | No | No | No | No
SIM-004 | ACDC_patient061 | training/patient061/patient061_4d.nii.gz | 1.367 x 1.367 | 10 | ED=1 (real); ES per official Info.cfg | No | No | No | No | No
SIM-005 | ACDC_patient081 | training/patient081/patient081_4d.nii.gz | 1.652 x 1.652 | 5 | ED=1 (real); ES per official Info.cfg | No | No | No | No | No
SIM-006 | SUNNYBROOK_SC-N-2 | SC-N-2 DICOM series (not yet retrieved) | N/A - not applicable (per-patient value not obtained) | 8 (dataset-wide constant) | NA - not released in public dataset metadata | No | No | No | No | No
SIM-007 | SUNNYBROOK_SC-HYP-1 | SC-HYP-1 DICOM series (not yet retrieved) | N/A - not applicable (per-patient value not obtained) | 8 (dataset-wide constant) | NA - not released in public dataset metadata | No | No | No | No | No
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | SC-HF-NI-3 DICOM series (not yet retrieved) | N/A - not applicable (per-patient value not obtained) | 8 (dataset-wide constant) | NA - not released in public dataset metadata | No | No | No | No | No
SIM-009 | SUNNYBROOK_SC-HF-I-1 | SC-HF-I-1 DICOM series (not yet retrieved) | N/A - not applicable (per-patient value not obtained) | 8 (dataset-wide constant) | NA - not released in public dataset metadata | No | No | No | No | No
SIM-010 | CAMUS_patient0001 | patient0001_2CH_sequence.mhd / patient0001_4CH_sequence.mhd (official naming) | 0.30 x 0.15 (fixed dataset-wide grid) | N/A - not applicable (2D imaging - no slice thickness) | NA - not released in public dataset metadata | No | No | No | No | No
Image_Loaded = No for all 10 subjects, including ACDC (files are publicly downloadable but have not actually been opened/loaded in this project). No interpolation has been applied to any value here.

## 4 Image Preprocessing
Simulation_ID | Subject_ID | Noise_Reduction | Intensity_Normalization | Resampling_Performed | Mask_Verification | Topology_Checking | Hole_Filling_Applied | Steps_Recorded
SIM-001 | ACDC_patient001 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-002 | ACDC_patient021 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-003 | ACDC_patient041 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-004 | ACDC_patient061 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-005 | ACDC_patient081 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-006 | SUNNYBROOK_SC-N-2 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-007 | SUNNYBROOK_SC-HYP-1 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-009 | SUNNYBROOK_SC-HF-I-1 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
SIM-010 | CAMUS_patient0001 | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | Not yet performed | N/A - no preprocessing has run yet
All preprocessing is deterministic by design (per project rule) and will be logged step-by-step here once actually run - original geometry is never to be altered beyond what is algorithmically required.

## 5 Geometry Reconstruction
Simulation_ID | Subject_ID | LV_Surface_Generated | RV_Surface_Generated | Epicardial_Surface_Generated | Myocardial_Shell_Generated | STL_Filename | VTK_Filename | PLY_Filename | Watertight_Verified | Surface_Normals_Verified | Non_Manifold_Check | Self_Intersection_Check | Surface_Area_cm2 | Enclosed_Volume_mL
SIM-001 | ACDC_patient001 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-002 | ACDC_patient021 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-003 | ACDC_patient041 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-004 | ACDC_patient061 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-005 | ACDC_patient081 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-006 | SUNNYBROOK_SC-N-2 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-007 | SUNNYBROOK_SC-HYP-1 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-009 | SUNNYBROOK_SC-HF-I-1 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
SIM-010 | CAMUS_patient0001 | No | No | No | No | Not generated | Not generated | Not generated (optional format) | No | No | No | No
Enclosed_Volume_mL here is the MESH-derived cavity volume once reconstruction is actually run - distinct from the dataset's mask-derived LV_EDV already reported in Digital_Twin_Simulation_Results_Workbook.xlsx Sheet 2. The two should agree closely once computed, but the mesh-derived value has not been computed for any subject and must not be pre-filled with the dataset value.

## 6 FE Mesh Generation
Simulation_ID | Subject_ID | Element_Type | Nodes | Elements | Aspect_Ratio | Skewness | Jacobian | Min_Quality | Avg_Quality | Max_Quality | Refinement_Performed | Optimization_Performed
SIM-001 | ACDC_patient001 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-002 | ACDC_patient021 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-003 | ACDC_patient041 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-004 | ACDC_patient061 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-005 | ACDC_patient081 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-006 | SUNNYBROOK_SC-N-2 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-007 | SUNNYBROOK_SC-HYP-1 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-009 | SUNNYBROOK_SC-HF-I-1 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
SIM-010 | CAMUS_patient0001 | Tetrahedral (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 3/COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | [8 empty] | No | No
Target quality thresholds (aspect ratio <= 5:1, Jacobian >= 0.3, skewness <= 0.6) are specified in Digital_Twin_Construction_Protocol_and_Simulation_Dataset_Specification.xlsx Sheet 5; actual measured values will populate here only once a real mesh is generated and reported.

## 7 Fiber Assignment
Simulation_ID | Subject_ID | Method | Atlas_Reference | Helix_Angle_Epi_deg | Helix_Angle_Endo_deg | Sheet_Angle_deg | Fiber_Vectors_Generated | Sheet_Vectors_Generated | Sheet_Normal_Vectors_Generated | Assignment_Status
SIM-001 | ACDC_patient001 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-002 | ACDC_patient021 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-003 | ACDC_patient041 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-004 | ACDC_patient061 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-005 | ACDC_patient081 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-006 | SUNNYBROOK_SC-N-2 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-007 | SUNNYBROOK_SC-HYP-1 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-009 | SUNNYBROOK_SC-HF-I-1 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
SIM-010 | CAMUS_patient0001 | Rule-based (Bayer, Blake, Plank & Trayanova 2012, Laplace-Dirichlet method) - planned method | No DT-MRI atlas used by default; rule-based generation is the recommended method since none of ACDC/Sunnybrook/CAMUS include diffusion tensor imaging | ~-60 (commonly cited transmural endpoint) | ~+60 to +80 (commonly cited transmural endpoint) | Model/method-dependent - no single published consensus value | No | No | No | Not started
Method and literature-cited angle ranges are real (see Simulation_Input_Parameter_Workbook.xlsx Sheet 4); no fiber field has actually been generated for any subject's mesh, since no mesh exists yet. No manual editing is planned per project rule - assignment is algorithmic only.

## 8 Material Properties
Property | Literature Value / Range | Provenance | Source | Assigned_in_COMSOL
Blood density | 1050-1060 kg/m^3 | Literature-derived | Consistently cited across cardiac/vascular CFD literature (e.g. 1060 kg/m^3) | No
Blood viscosity | 0.0035-0.004 Pa.s | Literature-derived | Newtonian approximation, consistently cited across cardiac CFD literature | No
Myocardial density | 1050-1081 kg/m^3 | Literature-derived | Cardiac biomechanics/CFD literature (soft tissue density approximation) | No
Passive myocardium (Holzapfel-Ogden a) | 0.059 kPa | Literature-derived / Constitutive model | Garcia-Blanco et al., as tabulated in arXiv:2009.03759 Table 4 | No
Passive myocardium (Holzapfel-Ogden af) | 18.472 kPa | Literature-derived / Constitutive model | Garcia-Blanco et al., as tabulated in arXiv:2009.03759 Table 4 | No
Passive myocardium (Guccione C) | 0.876-0.88 kPa | Literature-derived / Constitutive model | Guccione et al. 1991/1993, as cited in multiple subsequent studies | No
Passive myocardium (Guccione bf) | 18.46-18.48 | Literature-derived / Constitutive model | Guccione et al. 1991, as reused in PMC5924776 and US patent 10736989 | No
Values are real, literature-cited (Simulation_Input_Parameter_Workbook.xlsx Sheets 2-3) - never invented. None has yet been entered into an actual COMSOL model for any subject.

## 9 Electrophysiology
Simulation_ID | Subject_ID | EP_Included | Activation_Sequence | Purkinje_Initiation | Activation_Timing | Conduction_Velocity | Notes
SIM-001 | ACDC_patient001 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-002 | ACDC_patient021 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-003 | ACDC_patient041 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-004 | ACDC_patient061 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-005 | ACDC_patient081 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-006 | SUNNYBROOK_SC-N-2 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-007 | SUNNYBROOK_SC-HYP-1 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-009 | SUNNYBROOK_SC-HF-I-1 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
SIM-010 | CAMUS_patient0001 | No | N/A | N/A | N/A | N/A | Electrophysiology not included in current implementation.
Per project scope, EP modeling is optional/future work (Digital_Twin_Construction_Protocol...xlsx Sheet 6, Physics Interfaces) - explicitly documented as not included, per the project rule for undecided scope.

## 10 Boundary Conditions
Boundary / Parameter | Literature Value | Provenance | Source / Note | Assigned_in_COMSOL
LV pressure (ED) | 8-12 mmHg | Literature-derived | General adult clinical reference range | No
LV pressure (peak systolic) | ~120 mmHg | Literature-derived | General adult clinical reference range | No
RV pressure (ED) | 2-6 mmHg | Literature-derived | General adult clinical reference range | No
RV pressure (peak systolic) | 20-30 mmHg | Literature-derived | General adult clinical reference range | No
Mitral valve | Idealized open (diastole) / closed (systole) | Simulation assumption | No deformable valve model in current scope | No
Aortic valve | Idealized open (systole) / closed (diastole) | Simulation assumption | No deformable valve model in current scope | No
Windkessel parameters (Rp, Rd, C) | Not yet determined | To be calibrated | No literature consensus value identified for this cohort; requires dedicated calibration | No
Pericardial constraint | Not yet determined | To be calibrated | No single consensus literature value found | No
Values are real literature-derived ranges (Simulation_Input_Parameter_Workbook.xlsx Sheet 5) or explicitly flagged 'To be calibrated' where no literature consensus value was found. None assigned in an actual COMSOL model yet.

## 11 Gravity Implementation
Scenario | Acceleration | Vector (x, y, z) | Source | Applied_as_Body_Force | Other_Parameters_Changed
Earth | 9.80665 m/s^2 | (0, -9.80665, 0) | Standard gravity, exact SI definition (BIPM/NIST) | No | No - gravity is the sole independent variable across the 4 scenarios per design
Mars | 3.71 m/s^2 | (0, -3.71, 0) | Published Mars surface gravity (NASA/planetary science reference) | No | No - gravity is the sole independent variable across the 4 scenarios per design
Moon | 1.62 m/s^2 | (0, -1.62, 0) | Published lunar surface gravity (NASA/planetary science reference) | No | No - gravity is the sole independent variable across the 4 scenarios per design
Microgravity | 0 m/s^2 | (0, 0, 0) | Idealized zero-gravity condition | No | No - gravity is the sole independent variable across the 4 scenarios per design
Gravity values are exact physical constants (real, not estimated). Not yet applied inside an actual COMSOL model for any subject.

## 12 COMSOL Model Setup
Simulation_ID | Subject_ID | Geometry_Imported | Mesh_Imported | Materials_Imported | Physics_Configured | Boundary_Conditions_Imported | Gravity_Imported | Solver_Type | Residual_Tolerance | Solver_Iterations | Memory_Usage | CPU_Time
SIM-001 | ACDC_patient001 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-002 | ACDC_patient021 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-003 | ACDC_patient041 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-004 | ACDC_patient061 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-005 | ACDC_patient081 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-006 | SUNNYBROOK_SC-N-2 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-007 | SUNNYBROOK_SC-HYP-1 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-008 | SUNNYBROOK_SC-HF-NI-3 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-009 | SUNNYBROOK_SC-HF-I-1 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
SIM-010 | CAMUS_patient0001 | No | No | No | No | No | No | Time-dependent, fully coupled, adaptive time stepping (planned - Simulation_Input_Parameter_Workbook.xlsx Sheet 7)
No COMSOL model has been constructed for any subject. Residual tolerance, iterations, memory, and CPU time will only be recorded from an actual completed solver run.

## 13 Simulation Execution
Simulation_ID | Subject_ID | Dataset | Disease_Group | Gravity_Condition | Status | Converged | Runtime
SIM-001-EART | ACDC_patient001 | ACDC | DCM (Dilated Cardiomyopathy) | Earth | Not yet simulated
SIM-001-MARS | ACDC_patient001 | ACDC | DCM (Dilated Cardiomyopathy) | Mars | Not yet simulated
SIM-001-MOON | ACDC_patient001 | ACDC | DCM (Dilated Cardiomyopathy) | Moon | Not yet simulated
SIM-001-MICR | ACDC_patient001 | ACDC | DCM (Dilated Cardiomyopathy) | Microgravity | Not yet simulated
SIM-002-EART | ACDC_patient021 | ACDC | HCM (Hypertrophic Cardiomyopathy) | Earth | Not yet simulated
SIM-002-MARS | ACDC_patient021 | ACDC | HCM (Hypertrophic Cardiomyopathy) | Mars | Not yet simulated
SIM-002-MOON | ACDC_patient021 | ACDC | HCM (Hypertrophic Cardiomyopathy) | Moon | Not yet simulated
SIM-002-MICR | ACDC_patient021 | ACDC | HCM (Hypertrophic Cardiomyopathy) | Microgravity | Not yet simulated
SIM-003-EART | ACDC_patient041 | ACDC | MINF (Myocardial Infarction) | Earth | Not yet simulated
SIM-003-MARS | ACDC_patient041 | ACDC | MINF (Myocardial Infarction) | Mars | Not yet simulated
SIM-003-MOON | ACDC_patient041 | ACDC | MINF (Myocardial Infarction) | Moon | Not yet simulated
SIM-003-MICR | ACDC_patient041 | ACDC | MINF (Myocardial Infarction) | Microgravity | Not yet simulated
SIM-004-EART | ACDC_patient061 | ACDC | NOR (Normal) | Earth | Not yet simulated
SIM-004-MARS | ACDC_patient061 | ACDC | NOR (Normal) | Mars | Not yet simulated
SIM-004-MOON | ACDC_patient061 | ACDC | NOR (Normal) | Moon | Not yet simulated
SIM-004-MICR | ACDC_patient061 | ACDC | NOR (Normal) | Microgravity | Not yet simulated
SIM-005-EART | ACDC_patient081 | ACDC | RV (Abnormal Right Ventricle) | Earth | Not yet simulated
SIM-005-MARS | ACDC_patient081 | ACDC | RV (Abnormal Right Ventricle) | Mars | Not yet simulated
SIM-005-MOON | ACDC_patient081 | ACDC | RV (Abnormal Right Ventricle) | Moon | Not yet simulated
SIM-005-MICR | ACDC_patient081 | ACDC | RV (Abnormal Right Ventricle) | Microgravity | Not yet simulated
SIM-006-EART | SUNNYBROOK_SC-N-2 | Sunnybrook | N (Normal) | Earth | Not yet simulated
SIM-006-MARS | SUNNYBROOK_SC-N-2 | Sunnybrook | N (Normal) | Mars | Not yet simulated
SIM-006-MOON | SUNNYBROOK_SC-N-2 | Sunnybrook | N (Normal) | Moon | Not yet simulated
SIM-006-MICR | SUNNYBROOK_SC-N-2 | Sunnybrook | N (Normal) | Microgravity | Not yet simulated
SIM-007-EART | SUNNYBROOK_SC-HYP-1 | Sunnybrook | HYP (Hypertrophy) | Earth | Not yet simulated
SIM-007-MARS | SUNNYBROOK_SC-HYP-1 | Sunnybrook | HYP (Hypertrophy) | Mars | Not yet simulated
SIM-007-MOON | SUNNYBROOK_SC-HYP-1 | Sunnybrook | HYP (Hypertrophy) | Moon | Not yet simulated
SIM-007-MICR | SUNNYBROOK_SC-HYP-1 | Sunnybrook | HYP (Hypertrophy) | Microgravity | Not yet simulated
SIM-008-EART | SUNNYBROOK_SC-HF-NI-3 | Sunnybrook | HF (Heart Failure without infarction) | Earth | Not yet simulated
SIM-008-MARS | SUNNYBROOK_SC-HF-NI-3 | Sunnybrook | HF (Heart Failure without infarction) | Mars | Not yet simulated
SIM-008-MOON | SUNNYBROOK_SC-HF-NI-3 | Sunnybrook | HF (Heart Failure without infarction) | Moon | Not yet simulated
SIM-008-MICR | SUNNYBROOK_SC-HF-NI-3 | Sunnybrook | HF (Heart Failure without infarction) | Microgravity | Not yet simulated
SIM-009-EART | SUNNYBROOK_SC-HF-I-1 | Sunnybrook | HF-I (Heart Failure with Infarction) | Earth | Not yet simulated
SIM-009-MARS | SUNNYBROOK_SC-HF-I-1 | Sunnybrook | HF-I (Heart Failure with Infarction) | Mars | Not yet simulated
SIM-009-MOON | SUNNYBROOK_SC-HF-I-1 | Sunnybrook | HF-I (Heart Failure with Infarction) | Moon | Not yet simulated
SIM-009-MICR | SUNNYBROOK_SC-HF-I-1 | Sunnybrook | HF-I (Heart Failure with Infarction) | Microgravity | Not yet simulated
SIM-010-EART | CAMUS_patient0001 | CAMUS | Not released in public metadata (cohort-level only) | Earth | Not yet simulated
SIM-010-MARS | CAMUS_patient0001 | CAMUS | Not released in public metadata (cohort-level only) | Mars | Not yet simulated
SIM-010-MOON | CAMUS_patient0001 | CAMUS | Not released in public metadata (cohort-level only) | Moon | Not yet simulated
SIM-010-MICR | CAMUS_patient0001 | CAMUS | Not released in public metadata (cohort-level only) | Microgravity | Not yet simulated
40 rows = 10 subjects x 4 gravity conditions. All Status = 'Not yet simulated'. Identical run-ID scheme to Digital_Twin_Simulation_Results_Workbook.xlsx Sheet 1 for direct traceability once real runs occur.

## 14 Numerical Output Export
Output Category | Variables Included | Export Format | Status | Stored In
Geometry | LV/RV cavity volume, wall thickness, surface area | CSV / COMSOL report | Not yet performed | Digital_Twin_Simulation_Results_Workbook.xlsx Sheet 2
Mechanics | Pressure, wall stress, fiber stress, myocardial strain, principal strain, stress tensor | CSV / COMSOL report | Not yet performed | Digital_Twin_Simulation_Results_Workbook.xlsx Sheet 4
Hemodynamics | Velocity vectors/magnitude, pressure field, wall shear stress, streamlines, cardiac output, stroke volume, EF | CSV / VTU / COMSOL report | Not yet performed | Digital_Twin_Simulation_Results_Workbook.xlsx Sheet 5
Functional | PV loop, ESPVR, EDPVR, peak LV/RV pressure, peak strain, peak stress | CSV / COMSOL report | Not yet performed | Digital_Twin_Simulation_Results_Workbook.xlsx Sheets 5 and 11
Time-dependent | ED, ES, peak systole, peak diastole, full cardiac cycle time series | CSV time series | Not yet performed | Digital_Twin_Simulation_Results_Workbook.xlsx Sheets 4-5
This sheet documents the EXPORT PROCESS and destination only. The master numerical store for every exported value is Digital_Twin_Simulation_Results_Workbook.xlsx - values are not duplicated here to avoid two sources of truth diverging.

## 15 Gravity Comparison
Comparison | Variable | Absolute_Difference | Percentage_Change | Effect_Size | Status
Earth vs Mars | (all Sheet 7 variables of Digital_Twin_Simulation_Results_Workbook.xlsx) |  |  |  | Not yet computed
Earth vs Moon | (all Sheet 7 variables of Digital_Twin_Simulation_Results_Workbook.xlsx) |  |  |  | Not yet computed
Earth vs Microgravity | (all Sheet 7 variables of Digital_Twin_Simulation_Results_Workbook.xlsx) |  |  |  | Not yet computed
Mars vs Moon | (all Sheet 7 variables of Digital_Twin_Simulation_Results_Workbook.xlsx) |  |  |  | Not yet computed
Mars vs Microgravity | (all Sheet 7 variables of Digital_Twin_Simulation_Results_Workbook.xlsx) |  |  |  | Not yet computed
Moon vs Microgravity | (all Sheet 7 variables of Digital_Twin_Simulation_Results_Workbook.xlsx) |  |  |  | Not yet computed
Not yet computed - no simulation results exist to compare. Once Sheet 13 runs are complete and populate Digital_Twin_Simulation_Results_Workbook.xlsx, these 6 pairwise comparisons should be computed automatically (script, not manual calculation) for every relevant output variable.

## 16 Validation
Comparator Type | Reference | RMSE | MAE | Relative_Error | R2 | Bias | Limits_of_Agreement | Status
Dataset-derived measurement | ACDC LV_EDV/ESV/EF (real, resolved values) | [6 empty] | Not yet evaluated
Published physiological reference | General clinical normal/pathological EF, pressure ranges (Simulation_Input_Parameter_Workbook.xlsx Sheet 9) | [6 empty] | Not yet evaluated
Astronaut study | Specific reference study not yet identified/selected | [6 empty] | Not yet evaluated
Bed-rest study | Specific reference study not yet identified/selected | [6 empty] | Not yet evaluated
Astronaut/bed-rest comparator studies are deliberately left as 'not yet identified' rather than citing specific papers that were not verified in this project - selecting appropriate reference studies is real work for the validation phase, not something to fill in speculatively now.

## 17 Quality Control
QC Item | Status | Evidence | Flagged_Issues
Geometry integrity | Not checked | N/A - upstream stage not yet performed | None
Mesh integrity | Not checked | N/A - upstream stage not yet performed | None
Solver convergence | Not checked | N/A - upstream stage not yet performed | None
Boundary conditions | Not checked | N/A - upstream stage not yet performed | None
Material assignment | Not checked | N/A - upstream stage not yet performed | None
Fiber orientation | Not checked | N/A - upstream stage not yet performed | None
Gravity vector | Not checked | N/A - upstream stage not yet performed | None
Numerical stability | Not checked | N/A - upstream stage not yet performed | None
Simulation reproducibility | Not checked | N/A - upstream stage not yet performed | None
Gravity vector is the one item that COULD be checked now (Sheet 11 values are exact constants) but is marked 'Not checked' because it has not actually been verified inside a constructed COMSOL model yet.

## 18 Execution Log
Date | Simulation_ID | Phase | Operator | Action | Result | Notes
Empty log - add one row per actual pipeline action as execution begins (e.g. 'Phase 3 geometry reconstruction started for SIM-001').

## 19 Software and Versions
Software | Purpose | Version | Status
COMSOL Multiphysics | Primary FE simulation platform | To be recorded at implementation | Planned
Python | Preprocessing, meshing scripts, post-processing | 3.x - To be recorded at implementation | In use (cohort harmonization only)
MATLAB (if used) | Optional auxiliary analysis / LiveLink automation | To be recorded at implementation | Not yet in use
3D Slicer | Segmentation review, surface extraction | To be recorded at implementation | Planned
VTK | Surface extraction, mesh manipulation | To be recorded at implementation | Planned
Gmsh | Alternative open-source mesh generator | To be recorded at implementation | Planned (optional)
Version numbers deliberately read 'To be recorded at implementation' rather than a specific number, since no software has actually been run for this pipeline yet.

## 20 README
Patient-Specific Digital Twin Execution Pipeline Workbook
STATUS: This is the pre-execution pipeline workbook - the final specification and tracking layer before
actual COMSOL simulations are run. No image has been loaded, no geometry reconstructed, no mesh
generated, and no simulation executed for any of the 10 representative subjects.
Representative cohort (Sheet 2) is IDENTICAL to Simulation_Subject_Execution_Workbook.xlsx Sheet 1 - 5
ACDC + 4 Sunnybrook + 1 CAMUS - kept the same across workbooks specifically for traceability, per the
instruction to select representative patients exactly as already documented.
Real, source-verified content in this workbook:
- Sheet 3: real per-patient imaging parameters for the 5 ACDC subjects; real dataset-wide constants for
Sunnybrook and CAMUS
- Sheet 7: real literature-cited fiber method and angle ranges
- Sheet 8: real literature-cited material properties (blood density/viscosity, Holzapfel-Ogden and
Guccione constitutive parameters, each with its citation)
- Sheet 10: real literature-cited boundary condition ranges, or explicitly 'To be calibrated' where no
literature consensus was found
- Sheet 11: exact gravity physical constants for all 4 scenarios
Everything execution-status-related (Sheets 3-6, 9, 12, 13, 15, 16, 17) is honestly 'No' / 'Not yet
performed' / 'Not yet simulated' - nothing has been estimated or pre-filled with plausible numbers.
Sheet 14 (Numerical Output Export) deliberately does NOT duplicate the full 40-row x many-column output
table - that master store already exists in Digital_Twin_Simulation_Results_Workbook.xlsx. This sheet
documents the export process and points to where each category of value will actually live.
Sheet 16 (Validation) leaves astronaut/bed-rest comparator studies as 'not yet identified' rather than
citing specific papers that were not verified in this project - selecting the right reference studies is
real work for the validation phase itself.
Next real step: obtain actual imaging files for at least the 5 ACDC subjects (public, no registration) and
begin Phase 1 (Image Loading) for real.