## Simulation Overview
Simulation ID | Simulation Name | Objective | Dataset Source | Cardiac Model | Gravity Scenario | Simulation Type | Planned Status | Notes
SIM-01 | Baseline Earth | Establish reference structural/hemodynamic behavior under standard terrestrial gravity across all clinical groups. | ACDC, Sunnybrook, CAMUS (per Experimental Groups, Sheet 3) | Solid Mechanics (+/- CFD/FSI per Digital Twin Construction Protocol workbook, Sheet 6) | Earth (1 g) | Structural mechanics (time-dependent, full cardiac cycle) | Planned | Reference condition for all cross-gravity comparisons (Sheet 11).
SIM-02 | Mars | Assess structural/hemodynamic response under Mars surface gravity relative to Earth baseline. | Same geometry/group set as SIM-01 | Same as SIM-01 | Mars (0.38 g) | Structural mechanics (time-dependent) | Planned | Paired comparison with SIM-01 (Sheet 11).
SIM-03 | Moon | Assess structural/hemodynamic response under lunar surface gravity relative to Earth baseline. | Same geometry/group set as SIM-01 | Same as SIM-01 | Moon (0.16 g) | Structural mechanics (time-dependent) | Planned | Paired comparison with SIM-01 (Sheet 11).
SIM-04 | Microgravity | Assess structural/hemodynamic response under idealized zero-gravity (spaceflight) condition relative to Earth baseline. | Same geometry/group set as SIM-01 | Same as SIM-01 | Microgravity (0 g) | Structural mechanics (time-dependent) | Planned | Paired comparison with SIM-01 (Sheet 11).
SIM-05 | Sensitivity Analysis | Quantify how simulation outputs respond to variation in literature-derived/assumed parameters (heart rate, material stiffness, boundary pressure, fiber angle, blood viscosity, gravity level). | Single representative geometry per clinical group (subset of SIM-01-04 cases) | Same physics as SIM-01-04 | All four scenarios, parametrically varied per Sheet 10 | Structural mechanics, parametric sweep | Planned | Design specified in Sheet 10 (Sensitivity Analysis Plan); not yet executed.
SIM-06 | Validation Runs | Compare simulation-derived geometry/volume/EF against dataset-derived ground truth (ACDC resolved LV values) and mesh/solver convergence checks. | ACDC subset with resolved LV_EDV/ESV/EF (Master_Analytical_Cohort_Digital_Twin.xlsx) | Same as SIM-01 | Earth (1 g) only - validation is against a static/known reference, not a gravity comparison | Mesh independence, geometry validation, EF/volume comparison | Planned | Design specified in Sheet 9 (Validation Strategy); not yet executed.

## Gravity Scenarios
Scenario | Gravity Level | Acceleration (m/s^2) | Gravity Vector | Physiological Rationale | Reference
Earth | 1 g | 9.8066 | (0, -9.80665, 0) | Baseline terrestrial reference condition | Standard gravity, exact SI definition (BIPM/NIST)
Mars | 0.38 g | 3.71 | (0, -3.71, 0) | Reduced gravitational loading representative of Mars surface operations (relevant to planned crewed Mars missions) | Published Mars surface gravity (NASA/planetary science reference value)
Moon | 0.16 g | 1.62 | (0, -1.62, 0) | Further reduced gravitational loading representative of lunar surface operations (relevant to Artemis-era lunar missions) | Published lunar surface gravity (NASA/planetary science reference value)
Microgravity | 0 g | 0 | (0, 0, 0) | Idealized zero-gravity condition representative of orbital spaceflight (relevant to long-duration ISS/future missions) | Idealized zero-gravity condition; true orbital microgravity is ~1e-6 g residual, approximated as exactly 0 for baseline structural comparison

## Experimental Groups
Group ID | Clinical Group | Geometry Source | Expected Sample Source | Simulation Purpose
GRP-01 | Healthy | ACDC 'NOR' group geometry (dataset-derived, once Geometry Construction Pipeline is run) | ACDC: 20 of 100 subjects (NOR group, per Master_Analytical_Cohort_Digital_Twin.xlsx) | Reference/normal structural and functional baseline for all disease-group comparisons
GRP-02 | Dilated Cardiomyopathy | ACDC 'DCM' group geometry | ACDC: 20 of 100 subjects (DCM group) | Assess gravity effects in a dilated, volume-overloaded ventricle geometry
GRP-03 | Hypertrophic Cardiomyopathy | ACDC 'HCM' group geometry / Sunnybrook 'HYP' group geometry | ACDC: 20 of 100 subjects (HCM group); Sunnybrook: 12 of 45 subjects (HYP group) | Assess gravity effects in a thickened-wall, pressure-adapted ventricle geometry, with two independent geometry sources for cross-dataset comparison
GRP-04 | Myocardial Infarction | ACDC 'MINF' group geometry / Sunnybrook 'HF-I' group geometry (heart failure with infarction) | ACDC: 20 of 100 subjects (MINF group); Sunnybrook: 12 of 45 subjects (HF-I group) | Assess gravity effects with regionally heterogeneous (infarcted vs. remote) myocardial material properties
GRP-05 | Heart Failure | ACDC 'MINF'/'DCM' groups combined per general HF phenotype / Sunnybrook 'HF' group geometry (heart failure without infarction) | Sunnybrook: 12 of 45 subjects (HF group); ACDC subjects with dataset-derived low LV_EF_percent as a cross-dataset supplement | Assess gravity effects in reduced-EF geometries broadly, independent of specific infarct/dilation etiology
GRP-06 | Normal Echocardiography | CAMUS subjects without the cohort-level pathological EF<45% flag (dataset-wide statistic: ~50% of the 500-subject CAMUS cohort) | CAMUS: up to ~250 of 500 subjects (exact per-subject classification pending - see Master_Analytical_Cohort_Digital_Twin.xlsx Sheet 1, Disease_Category column, currently NA per-subject for CAMUS) | Extend gravity comparison to an independent imaging modality (2D echocardiography) and the largest available sample size

## Independent Variables
Variable | Unit | Type | Source | Adjustable
Gravity | m/s^2 | Categorical (4 levels: Earth/Mars/Moon/Microgravity) | Physical constant (Sheet 2) | Yes - primary experimental factor
Heart Rate | bpm | Continuous | Literature-derived population range (Simulation_Input_Parameter_Workbook.xlsx Sheet 1: 60-100 bpm; not available per-subject in any of the three datasets) | Yes (within Sheet 10 sensitivity range)
Blood Density | kg/m^3 | Continuous (held near-constant; literature range narrow) | Literature-derived (Simulation_Input_Parameter_Workbook.xlsx Sheet 1: 1050-1060 kg/m^3) | Limited - literature-agreed narrow range
Blood Viscosity | Pa.s | Continuous (held near-constant; literature range narrow) | Literature-derived (Simulation_Input_Parameter_Workbook.xlsx Sheet 1: 0.0035-0.004 Pa.s) | Yes (within Sheet 10 sensitivity range)
Pressure | mmHg | Continuous / time-varying | Literature-derived (Simulation_Input_Parameter_Workbook.xlsx Sheet 5: ED ~8-12, peak systolic ~120 mmHg LV) | Yes (within Sheet 10 sensitivity range)
Passive Stiffness | kPa (constitutive model parameters) | Continuous, model-dependent | Constitutive model (Simulation_Input_Parameter_Workbook.xlsx Sheet 3: Holzapfel-Ogden or Guccione) | Yes (within Sheet 10 sensitivity range)
Active Tension | kPa | Continuous, model-dependent | Constitutive model (Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Yes (within Sheet 10 sensitivity range)
Fiber Orientation | degrees (helix angle) | Continuous field (spatially varying) | Literature-derived / rule-based method (Simulation_Input_Parameter_Workbook.xlsx Sheet 4) | Yes (within Sheet 10 sensitivity range)
Wall Thickness | mm | Continuous | Dataset-derived, once Surface Reconstruction is run (subject-specific geometry) | No - determined by subject geometry, not independently set
LV Geometry | mesh/surface (dimensionless) | Categorical (per subject/clinical group) | Dataset-derived (ACDC, Sunnybrook, CAMUS segmentation) | No - fixed per experimental group (Sheet 3)
RV Geometry | mesh/surface (dimensionless) | Categorical (per subject, ACDC only) | Dataset-derived (ACDC segmentation only) | No - fixed per subject; not applicable to Sunnybrook/CAMUS-based groups

## Controlled Variables
Variable | Control Method | Reason
Mesh density | Fixed at the converged density identified by the mesh independence study (Sheet 9) before any cross-scenario comparison begins | Prevents mesh-density differences from confounding gravity-scenario comparisons
Solver | Same solver type, tolerance, and iteration settings (per Simulation_Input_Parameter_Workbook.xlsx Sheet 7 / COMSOL_Model_Implementation_Workbook.xlsx Sheet 11) used identically across all scenarios for a given experiment | Ensures observed differences reflect the physics being compared, not solver configuration differences
Time step | Same time step used across all scenarios within a given experiment, fixed after the time-step convergence check | Prevents temporal discretization differences from confounding results
Convergence tolerance | Same relative/absolute tolerance applied across all scenarios within a given experiment | Ensures equivalent numerical accuracy across compared scenarios
Geometry smoothing | Same smoothing algorithm and parameters (per COMSOL_Model_Implementation_Workbook.xlsx Sheet 4) applied identically to every subject's geometry | Prevents smoothing-induced geometric variation from confounding group/scenario comparisons
Material assignment | Same constitutive model and parameter set held fixed across gravity scenarios for a given clinical group (only gravity varies within a SIM-01-04 comparison set) | Isolates gravity as the independent variable of interest
Boundary conditions | Same boundary condition type and value held fixed across gravity scenarios for a given clinical group (per Simulation_Input_Parameter_Workbook.xlsx Sheet 5) | Isolates gravity as the independent variable of interest

## Simulation Matrix
Experiment ID | Clinical Group | Gravity | Heart Rate | Geometry | Material Model | Boundary Conditions | Expected Outputs | Status
EXP-001 | Healthy | Earth (1 g) | 60-100 bpm (literature range - see Sheet 4) | Healthy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-002 | Healthy | Mars (0.38 g) | 60-100 bpm (literature range - see Sheet 4) | Healthy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-003 | Healthy | Moon (0.16 g) | 60-100 bpm (literature range - see Sheet 4) | Healthy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-004 | Healthy | Microgravity (0 g) | 60-100 bpm (literature range - see Sheet 4) | Healthy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-005 | Dilated Cardiomyopathy | Earth (1 g) | 60-100 bpm (literature range - see Sheet 4) | Dilated Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-006 | Dilated Cardiomyopathy | Mars (0.38 g) | 60-100 bpm (literature range - see Sheet 4) | Dilated Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-007 | Dilated Cardiomyopathy | Moon (0.16 g) | 60-100 bpm (literature range - see Sheet 4) | Dilated Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-008 | Dilated Cardiomyopathy | Microgravity (0 g) | 60-100 bpm (literature range - see Sheet 4) | Dilated Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-009 | Hypertrophic Cardiomyopathy | Earth (1 g) | 60-100 bpm (literature range - see Sheet 4) | Hypertrophic Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-010 | Hypertrophic Cardiomyopathy | Mars (0.38 g) | 60-100 bpm (literature range - see Sheet 4) | Hypertrophic Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-011 | Hypertrophic Cardiomyopathy | Moon (0.16 g) | 60-100 bpm (literature range - see Sheet 4) | Hypertrophic Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-012 | Hypertrophic Cardiomyopathy | Microgravity (0 g) | 60-100 bpm (literature range - see Sheet 4) | Hypertrophic Cardiomyopathy group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-013 | Myocardial Infarction | Earth (1 g) | 60-100 bpm (literature range - see Sheet 4) | Myocardial Infarction group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-014 | Myocardial Infarction | Mars (0.38 g) | 60-100 bpm (literature range - see Sheet 4) | Myocardial Infarction group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-015 | Myocardial Infarction | Moon (0.16 g) | 60-100 bpm (literature range - see Sheet 4) | Myocardial Infarction group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-016 | Myocardial Infarction | Microgravity (0 g) | 60-100 bpm (literature range - see Sheet 4) | Myocardial Infarction group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-017 | Heart Failure | Earth (1 g) | 60-100 bpm (literature range - see Sheet 4) | Heart Failure group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-018 | Heart Failure | Mars (0.38 g) | 60-100 bpm (literature range - see Sheet 4) | Heart Failure group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-019 | Heart Failure | Moon (0.16 g) | 60-100 bpm (literature range - see Sheet 4) | Heart Failure group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-020 | Heart Failure | Microgravity (0 g) | 60-100 bpm (literature range - see Sheet 4) | Heart Failure group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-021 | Normal Echocardiography | Earth (1 g) | 60-100 bpm (literature range - see Sheet 4) | Normal Echocardiography group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-022 | Normal Echocardiography | Mars (0.38 g) | 60-100 bpm (literature range - see Sheet 4) | Normal Echocardiography group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-023 | Normal Echocardiography | Moon (0.16 g) | 60-100 bpm (literature range - see Sheet 4) | Normal Echocardiography group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned
EXP-024 | Normal Echocardiography | Microgravity (0 g) | 60-100 bpm (literature range - see Sheet 4) | Normal Echocardiography group geometry (Sheet 3) | Holzapfel-Ogden or Guccione (final selection pending - Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Per Simulation_Input_Parameter_Workbook.xlsx Sheet 5 (pressure, valve, base, pericardial) | Displacement, stress, strain fields; LV volume/EF time course (see Sheet 7 for full output list) | Planned

## Planned Output Variables
Output Variable | Unit | Clinical Importance | Primary Endpoint | Secondary Endpoint
LV EDV | mL | Core clinical volumetric measure; primary determinant of preload | Yes | No
LV ESV | mL | Core clinical volumetric measure; reflects contractile emptying | Yes | No
Stroke Volume | mL | Directly relates to cardiac output and pump performance | Yes | No
Ejection Fraction | % | Primary clinical indicator of systolic function | Yes | No
Pressure | Pa (or mmHg) | Drives mechanical loading; central to PV-loop interpretation | Yes | No
Wall Stress | Pa (or kPa) | Reflects mechanical burden on the myocardium; relevant to remodeling risk | No | Yes
Wall Strain | dimensionless (or %) | Reflects regional deformation; sensitive marker of contractile function | No | Yes
Wall Shear Stress | Pa | Relevant to endothelial biology and flow-related risk (CFD scenarios only) | No | Yes
Velocity | m/s | Characterizes intracavitary flow pattern (CFD scenarios only) | No | Yes
Vorticity | 1/s | Characterizes flow rotational structure, relevant to diastolic filling patterns (CFD scenarios only) | No | Yes
Cardiac Output | L/min | Integrates stroke volume and heart rate into overall pump performance | No | Yes
Myocardial Work | mJ (or J) | Integrates pressure and volume change over the cycle; relates to metabolic demand | No | Yes
Von Mises Stress | Pa (or kPa) | Scalar equivalent stress; commonly used engineering measure of mechanical loading severity | No | Yes
Principal Stress | Pa (or kPa) | Direction-specific loading; relevant to anisotropic failure/remodeling risk assessment | No | Yes
Principal Strain | dimensionless (or %) | Direction-specific deformation; relevant to regional function assessment | No | Yes

## Visualization Plan
Figure | Visualization | Software | Export Format | Purpose
Pressure maps | Surface/volume color plot over the cardiac cycle | COMSOL post-processing / ParaView | PNG/VTU + animation | Illustrate spatial pressure distribution and its evolution across the cycle
Velocity vectors | Vector field plot (arrow/glyph plot) on a cavity slice | COMSOL post-processing / ParaView | PNG/VTU + animation | Illustrate intracavitary flow direction and magnitude (CFD scenarios)
Streamlines | Streamline plot through the cavity | COMSOL post-processing / ParaView | PNG/VTU + animation | Illustrate flow path structure (CFD scenarios)
Stress maps | Surface color plot (Von Mises or principal stress) on the myocardial wall | COMSOL post-processing | PNG/VTU + animation | Illustrate spatial distribution of mechanical loading
Strain maps | Surface color plot (principal strain) on the myocardial wall | COMSOL post-processing | PNG/VTU + animation | Illustrate spatial distribution of deformation
PV loops | 2D line plot: cavity volume (x) vs. cavity pressure (y) over one cardiac cycle, one curve per gravity scenario | COMSOL Global Evaluation + Python/matplotlib | PNG/SVG (vector) + underlying data as CSV | Primary comparative figure for gravity-scenario functional differences
3D geometry | Rendered 3D surface of reconstructed LV/RV/myocardium per clinical group | ParaView / 3D Slicer | PNG/STL | Illustrate the anatomical basis of each experimental group
Mesh | Rendered volumetric mesh with quality metric overlay | COMSOL post-processing / ParaView | PNG | Illustrate mesh quality and support the mesh independence validation claim
Animations | Time-sequenced render of deformation/field results across the cardiac cycle | COMSOL Animation export / ParaView | AVI/MP4/GIF | Supplementary video material illustrating dynamic behavior

## Validation Strategy
Validation Step | Comparator | Acceptance Criterion | Method | Status
Mesh independence | Key output variable (e.g. peak wall stress) across successive mesh refinement levels | < 5% change between the two finest refinement levels tested | Systematic mesh refinement study prior to production runs | Planned
Solver convergence | Solver residual norm across iterations/time steps | Residual below configured tolerance (Simulation_Input_Parameter_Workbook.xlsx Sheet 7) | Monitor COMSOL solver convergence log for every run | Planned
Literature comparison | Simulation-derived PV loop shape and stress/strain order of magnitude vs. published cardiac FE modeling studies | Qualitative shape/magnitude consistency (no subject-specific quantitative target exists for stress/strain - see Simulation_Input_Parameter_Workbook.xlsx Sheet 9) | Qualitative comparison against cited reference studies | Planned
Dataset comparison | Simulation-derived LV volume/EF vs. dataset-derived LV_EDV/ESV/EF_percent (ACDC, resolved values) | Volume within 5-10%; EF within 5 percentage points (Simulation_Input_Parameter_Workbook.xlsx Sheet 9) | Direct numerical comparison | Planned
Sensitivity analysis | Output variable response across the parameter ranges defined in Sheet 10 | Study-dependent; documents which parameters most influence outputs rather than a pass/fail threshold | Parametric sweep per Sheet 10 | Planned
Internal consistency | Cross-check that formula-derived quantities (SV=EDV-ESV, EF=SV/EDV*100) match directly-computed simulation outputs | Exact match (formula identity, not a tolerance-based comparison) | Automated post-processing script check | Planned

## Sensitivity Analysis Plan
Parameter | Range | Increment | Reason
Heart rate | 60-100 bpm | 10 bpm | Literature population range (Simulation_Input_Parameter_Workbook.xlsx Sheet 1); no per-subject value available in any of the three datasets
Gravity | 0-9.80665 m/s^2 (the four defined scenarios, Sheet 2) | Discrete scenario levels only (Earth/Mars/Moon/Microgravity) - not a continuous sweep | Gravity is the primary experimental factor (Sheet 4); its four levels are fixed by mission-relevant physical constants, not swept continuously
Material stiffness | Literature-reported range per constitutive model (Simulation_Input_Parameter_Workbook.xlsx Sheet 3: e.g. Holzapfel-Ogden af 18.472 kPa as a reported point estimate, varied +/-50% as a bracketing sweep given known inter-subject variability) | 25% steps across the bracketing range | Quantify how much uncertainty in literature-derived stiffness propagates to simulation outputs, given documented high inter-study/inter-subject variability (Simulation_Input_Parameter_Workbook.xlsx Sheet 3 notes)
Blood viscosity | 0.0035-0.004 Pa.s (literature range, Simulation_Input_Parameter_Workbook.xlsx Sheet 1) | 0.0005 Pa.s | Test sensitivity of CFD-scenario outputs to the narrow literature-reported range
Boundary pressure | ED 8-12 mmHg; peak systolic 100-140 mmHg (literature range, Simulation_Input_Parameter_Workbook.xlsx Sheet 5) | 10 mmHg (peak systolic); 1 mmHg (ED) | Quantify sensitivity to the literature-reported physiological pressure range, since no subject-specific pressure measurement exists in any of the three datasets
Fiber angle | Epicardium ~-60deg to Endocardium ~+60 to +80deg transmural range (Simulation_Input_Parameter_Workbook.xlsx Sheet 4), endpoints varied +/-10deg | 10 degrees | Quantify sensitivity to the commonly-cited transmural range endpoints, since no DT-MRI fiber measurement exists in any of the three datasets

## Statistical Analysis Plan
Comparison | Statistical Test | Outcome | Assumption
Earth vs Mars | Paired comparison (e.g. paired t-test or Wilcoxon signed-rank test, per-subject/per-geometry pairing across the two gravity scenarios) | Primary/secondary output variables (Sheet 7), compared within the same geometry across gravity levels | Normality to be assessed (Shapiro-Wilk or similar) before choosing parametric vs. non-parametric test; assumes each geometry is run under both scenarios (paired design)
Earth vs Moon | Same paired comparison approach as Earth vs Mars | Same as Earth vs Mars | Same as Earth vs Mars
Earth vs Microgravity | Same paired comparison approach as Earth vs Mars | Same as Earth vs Mars | Same as Earth vs Mars
Healthy vs Disease | Unpaired comparison across clinical groups (e.g. one-way ANOVA or Kruskal-Wallis across the 6 groups in Sheet 3, with post-hoc pairwise tests) | Primary/secondary output variables (Sheet 7), compared across clinical groups within a fixed gravity scenario | Independence between subjects/groups; normality and equal-variance assumptions to be checked before choosing parametric vs. non-parametric test
MRI vs Echocardiography | Unpaired comparison between MRI-derived groups (ACDC, Sunnybrook) and echocardiography-derived group (CAMUS) | Comparable output variables only (e.g. LV EF, LV volumes) - modality-specific outputs (e.g. RV volumes, only from ACDC) excluded from this specific comparison | Assumes cross-modality geometry reconstruction produces comparable functional outputs, which is itself a methodological assumption to be reported as a limitation, not a validated equivalence
Repeated scenario analysis | Repeated-measures ANOVA (or its non-parametric equivalent, Friedman test) across all four gravity scenarios within each subject/geometry | Primary/secondary output variables (Sheet 7), tracked across all four gravity levels per geometry | Sphericity assumption to be checked (Mauchly's test) for repeated-measures ANOVA; Friedman test used as a non-parametric fallback if violated

## Expected Physiological Changes
Gravity Scenario | Expected Effect | Mechanism | Evidence Source
Mars / Moon / Microgravity (reduced gravity, general trend) | Reduced preload | Lower gravitational hydrostatic gradient is expected to alter venous return distribution relative to the upright terrestrial condition, per general spaceflight/cardiovascular physiology literature | General spaceflight physiology literature (qualitative expectation; not a dataset- or simulation-derived prediction)
Mars / Moon / Microgravity (reduced gravity, general trend) | Reduced afterload | Reduced gravitational body force on blood columns is expected to lower the hydrostatic component of vascular resistance, per general spaceflight physiology literature | General spaceflight physiology literature (qualitative expectation)
Mars / Moon / Microgravity (reduced gravity, general trend) | Stroke volume change (direction not predicted quantitatively) | Altered preload/afterload balance is expected to shift stroke volume from the Earth-baseline value; published spaceflight studies report both acute increases and longer-term decreases depending on adaptation timescale, so this project does not commit to a single predicted direction | General spaceflight cardiovascular physiology literature (mixed/timescale-dependent findings reported)
Microgravity specifically | Cardiac output change (direction not predicted quantitatively) | Longitudinal spaceflight literature reports cardiac deconditioning over extended microgravity exposure, but this project models only the instantaneous mechanical loading effect of a single simulated cardiac cycle, not longitudinal physiological adaptation - so a specific predicted change is not stated | General spaceflight physiology literature; explicitly noted as a scope limitation of this project's instantaneous-loading simulation approach
Mars / Moon / Microgravity (reduced gravity, general trend) | Wall stress alteration (direction not predicted quantitatively) | Altered pressure loading and body-force distribution under reduced gravity is expected to shift the myocardial wall stress distribution relative to Earth baseline; the specific pattern depends on the interaction between geometry, material properties, and pressure boundary conditions, which this project has not yet simulated | Biomechanical first-principles reasoning (body force scales cavity loading); no subject-specific or literature-quantified prediction is made
Mars / Moon / Microgravity (reduced gravity, general trend) | Flow redistribution (CFD/FSI scenarios) | Reduced gravitational body force on the blood column is expected to alter intracavitary flow patterns relative to Earth baseline, per general fluid-dynamics first-principles reasoning | Biomechanical/fluid-dynamics first-principles reasoning; no subject-specific or literature-quantified prediction is made

## Simulation Timeline
Phase | Task | Estimated Duration | Dependency | Status
Geometry | Run Geometry Construction Pipeline (segmentation import through STL export) for all planned experimental groups | Dependent on raw file access for Sunnybrook/CAMUS (currently blocked); ACDC alone estimated at several hours to days of processing time once started - not yet benchmarked | Raw imaging file access (Sunnybrook/CAMUS currently gated/blocked; see Master_Analytical_Cohort_Digital_Twin.xlsx) | Planned
Mesh | Generate and validate volumetric meshes for all reconstructed geometries | Not yet benchmarked - dependent on final mesh density decisions (Sheet 5, Sheet 9) | Geometry phase complete | Planned
Material | Assign material properties, constitutive model, and fiber orientation to each mesh | Not yet benchmarked | Mesh phase complete; constitutive model final selection (Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Planned
Simulation | Execute all planned experiments in the Simulation Matrix (Sheet 6) | Not yet benchmarked - dependent on final mesh size and solver settings | Material phase complete; solver configuration finalized (COMSOL_Model_Implementation_Workbook.xlsx Sheet 11) | Planned
Validation | Execute the Validation Strategy (Sheet 9) against completed simulation runs | Not yet benchmarked | Simulation phase complete for at least the relevant validation subset | Planned
Analysis | Execute the Statistical Analysis Plan (Sheet 11) on validated simulation outputs | Not yet benchmarked | Validation phase complete | Planned
Figures | Produce the figures specified in the Visualization Plan (Sheet 8) and Manuscript Figure and Table Planning (Sheet 19) | Not yet benchmarked | Analysis phase complete | Planned
Manuscript | Draft and finalize manuscript Methods/Results incorporating validated findings | Not yet benchmarked | Figures phase complete | Planned

## Computational Resource Plan
Simulation | CPU | GPU | RAM | Estimated Runtime | Storage | Status
SIM-01 Baseline Earth (per experiment in Sheet 6) | >= 8-16 cores recommended (per COMSOL general guidance) | Not required for structural solvers | >= 16-32 GB (mesh-size-dependent, not yet finalized) | Not yet benchmarked - no simulation has been run | Several GB per run (result file size mesh/output-dependent) | Planned
SIM-02 Mars / SIM-03 Moon / SIM-04 Microgravity | Same as SIM-01 (identical mesh/solver configuration per Sheet 5 Controlled Variables) | Same as SIM-01 | Same as SIM-01 | Not yet benchmarked; expected to be comparable to SIM-01 given identical mesh/solver settings (only gravity load differs) | Same as SIM-01 | Planned
SIM-05 Sensitivity Analysis | Same per-run requirement as SIM-01, multiplied across the parameter sweep defined in Sheet 10 | Not required | Same per-run requirement as SIM-01 | Not yet benchmarked; total runtime scales with the number of sweep points defined in Sheet 10 | Scales with number of sweep runs | Planned
SIM-06 Validation Runs | Same as SIM-01, plus additional runs for mesh independence study (multiple refinement levels) | Not required | May exceed SIM-01 at the finest mesh refinement level tested | Not yet benchmarked | Scales with number of refinement levels tested | Planned

## Error Monitoring
Error Type | Detection Method | Correction | Severity
Solver divergence | Monitor COMSOL solver residual/error log during every run; automated flag if the nonlinear solver fails to converge within the configured maximum iterations | Apply load ramping/continuation methods; reduce time step; verify mesh quality first (a common root cause) | High - run must be discarded/rerun; no partial result is usable
Mesh inversion | COMSOL mesh quality check (negative or near-zero Jacobian elements) before and during large-deformation solves | Refine mesh in the affected region; reduce load step size; review geometry for problematic thin/sharp features | High - invalidates the affected simulation region/run
Negative volume | Automated post-processing check: computed cavity volume must remain positive at every time step | Indicates a mesh inversion or solver instability upstream - trace back to the originating cause rather than discarding the check itself | High - indicates a fundamentally invalid solution state
Convergence failure | Solver fails to meet the configured tolerance (Simulation_Input_Parameter_Workbook.xlsx Sheet 7) within the maximum iteration budget | Loosen tolerance only as a diagnostic step (not for production results); primarily address via load ramping, mesh refinement, or solver/Newton damping adjustment | Medium-High - run is not usable until resolved
Boundary condition errors | Quality Assurance check (Sheet 17): review every applied boundary condition against Simulation_Input_Parameter_Workbook.xlsx Sheet 5 before each run | Correct the specific misapplied boundary condition and rerun | Medium-High - produces a physiologically invalid result if undetected

## Risk Register
Risk | Likelihood | Impact | Mitigation | Status
Poor segmentation | Medium (CAMUS officially documents 19% of its images as poor quality, per official dataset statistics) | Medium (affects reliability of geometry derived from affected subjects/frames within the Normal Echocardiography group specifically) | Flag and, where feasible, exclude or separately report on subjects/frames with documented poor image quality; do not treat all segmentations as equally reliable | Planned (known risk, documented; mitigation not yet applied since no geometry pipeline has run)
Missing parameters | High (confirmed - see Simulation_Input_Parameter_Workbook.xlsx for numerous 'To be calibrated'/blank cells, e.g. pericardial constraint stiffness, per-subject heart rate) | Medium-High (blocks or weakens specific physics/scenarios) | Use documented literature ranges where available; explicitly flag any assumption-based value in manuscript reporting; pursue calibration studies for genuinely unknown parameters before final production runs | Planned
Solver instability | Medium | High (prevents obtaining any simulation result for the affected run) | Load ramping/continuation methods; verify mesh quality first; tune Newton damping and tolerance | Planned (mitigation strategy defined, not yet tested against a real run)
Numerical oscillation | Medium | Medium-High (produces unreliable time-course results if undetected) | Time-step convergence study; implicit time-stepping (COMSOL default for structural mechanics); monitor solution stability across time steps | Planned
Long runtime | Medium (24 planned experiments in the core Simulation Matrix, Sheet 6, plus sensitivity/validation runs) | Medium (delays project timeline, Sheet 13) | Benchmark runtime on a single representative case before committing to the full matrix; consider mesh-density/scope trade-offs if runtime is prohibitive | Planned (no runtime has been benchmarked yet - see Sheet 14)

## Quality Assurance
Quality Check | Method | Evidence | Status
Geometry | Visual review (ParaView/3D Slicer) + automated watertight/manifold check | Not yet available - no geometry has been constructed | Planned
Mesh | COMSOL/VTK mesh quality report (aspect ratio, skewness, Jacobian) reviewed against targets (COMSOL_Model_Implementation_Workbook.xlsx Sheet 5) | Not yet available - no mesh has been generated | Planned
Units | Explicit unit-conversion review (e.g. mmHg-to-Pa, kPa-to-Pa) for every parameter entering COMSOL | Not yet available - no simulation has been run | Planned
Material parameters | Cross-check every material parameter entered into COMSOL against Simulation_Input_Parameter_Workbook.xlsx Sheets 2-3 before each run | Not yet available | Planned
Boundary conditions | Cross-check every boundary condition entered into COMSOL against Simulation_Input_Parameter_Workbook.xlsx Sheet 5 before each run | Not yet available | Planned
Gravity vectors | Cross-check the applied gravity vector against Sheet 2 of this workbook for every run | Not yet available | Planned
Solver settings | Cross-check solver configuration against Simulation_Input_Parameter_Workbook.xlsx Sheet 7 / COMSOL_Model_Implementation_Workbook.xlsx Sheet 11 before each run | Not yet available | Planned
Output verification | Automated sanity check on every simulation output (e.g. positive volumes, EF between 0-100%, non-negative pressure magnitude where physiologically expected) before formal validation (Sheet 9) | Not yet available - no simulation has been run | Planned

## Reproducibility Plan
Item | Documentation Method | Repository | Status
COMSOL files | Archived .mph model file per experiment (Sheet 6), named by Experiment ID | Institutional storage + eventual public repository (GitHub/Zenodo, once created) | Planned
Python scripts | All preprocessing, meshing, fiber-generation, and post-processing analysis scripts, version-controlled | Git repository (recommended primary VC target) | Planned
Mesh | Archived volumetric mesh files per experiment | Institutional storage + manifest with checksums | Planned
Parameters | Simulation_Input_Parameter_Workbook.xlsx and this workbook's Sheets 2, 4-5, 10 (all input values and their provenance) | Supplementary Material + repository | Available now (parameter documentation, not simulation output)
Figures | All figures per the Visualization Plan (Sheet 8) and Manuscript Figure and Table Planning (Sheet 19), with generating script referenced | Repository + manuscript Supplementary Material | Planned
Supplementary tables | This workbook and its three companion workbooks (Digital Twin Construction Protocol, Simulation Input Parameter, COMSOL Model Implementation) | Manuscript Supplementary Material | Available now
README | Repository-level README describing project structure, dependencies, and how to reproduce each pipeline stage | Repository root | Planned - not yet written

## Manuscript Fig and Table Plan
Figure/Table | Description | Source | Status
Workflow (Figure) | Overall project pipeline diagram: cohort harmonization -> geometry -> mesh -> simulation -> validation -> analysis | Digital_Twin_Construction_Protocol...xlsx Sheet 1 | Planned (can be drafted now from existing workbook content)
Geometry (Figure) | Example reconstructed 3D LV/RV/myocardium geometry per experimental group (Sheet 3) | Geometry Construction Pipeline output (not yet run) | Planned - blocked pending pipeline execution
Mesh (Figure) | Volumetric mesh visualization with quality metric overlay | Mesh Implementation output (not yet run) | Planned - blocked
Pressure distribution (Figure) | Spatial pressure distribution at key cardiac cycle phases, compared across gravity scenarios | Simulation output (not yet run) | Planned - blocked
Velocity field (Figure) | Intracavitary blood velocity field visualization (CFD scenarios) | Simulation output (not yet run) | Planned - blocked
Wall stress (Figure) | Von Mises/principal stress distribution on the myocardial wall across gravity scenarios | Simulation output (not yet run) | Planned - blocked
Gravity comparison (Figure) | Side-by-side comparison of key output variables (Sheet 7) across all four gravity scenarios, per clinical group | Simulation output + Statistical Analysis Plan (Sheet 11) (not yet run) | Planned - blocked
PV loops (Figure) | Pressure-volume loop for each gravity scenario, overlaid per clinical group | Simulation output (not yet run) | Planned - blocked
Validation (Figure/Table) | Mesh independence, dataset-comparison, and sensitivity-analysis summary results (Sheet 9) | Validation Strategy execution (not yet run) | Planned - blocked
Cohort summary (Table) | Subject counts per dataset/clinical group (Sheet 3) | Master_Analytical_Cohort_Digital_Twin.xlsx | Available now
Parameter summary (Table) | Full material/boundary/solver parameter list with provenance tags | Simulation_Input_Parameter_Workbook.xlsx | Available now

## Experiment Execution Tracker
Experiment | Planned | Started | Completed | Validated | Notes
EXP-001 | Yes | No | No | No | Healthy / Earth (1 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-002 | Yes | No | No | No | Healthy / Mars (0.38 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-003 | Yes | No | No | No | Healthy / Moon (0.16 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-004 | Yes | No | No | No | Healthy / Microgravity (0 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-005 | Yes | No | No | No | Dilated Cardiomyopathy / Earth (1 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-006 | Yes | No | No | No | Dilated Cardiomyopathy / Mars (0.38 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-007 | Yes | No | No | No | Dilated Cardiomyopathy / Moon (0.16 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-008 | Yes | No | No | No | Dilated Cardiomyopathy / Microgravity (0 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-009 | Yes | No | No | No | Hypertrophic Cardiomyopathy / Earth (1 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-010 | Yes | No | No | No | Hypertrophic Cardiomyopathy / Mars (0.38 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-011 | Yes | No | No | No | Hypertrophic Cardiomyopathy / Moon (0.16 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-012 | Yes | No | No | No | Hypertrophic Cardiomyopathy / Microgravity (0 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-013 | Yes | No | No | No | Myocardial Infarction / Earth (1 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-014 | Yes | No | No | No | Myocardial Infarction / Mars (0.38 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-015 | Yes | No | No | No | Myocardial Infarction / Moon (0.16 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-016 | Yes | No | No | No | Myocardial Infarction / Microgravity (0 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-017 | Yes | No | No | No | Heart Failure / Earth (1 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-018 | Yes | No | No | No | Heart Failure / Mars (0.38 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-019 | Yes | No | No | No | Heart Failure / Moon (0.16 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-020 | Yes | No | No | No | Heart Failure / Microgravity (0 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-021 | Yes | No | No | No | Normal Echocardiography / Earth (1 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-022 | Yes | No | No | No | Normal Echocardiography / Mars (0.38 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-023 | Yes | No | No | No | Normal Echocardiography / Moon (0.16 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.
EXP-024 | Yes | No | No | No | Normal Echocardiography / Microgravity (0 g) - awaiting Geometry/Mesh/Material pipeline completion before this experiment can start.

## README
Gravity Simulation Experiment Design Workbook
This workbook is an EXPERIMENTAL DESIGN document. It defines every planned gravity simulation before execution: scenarios, experimental variables, comparison groups, outcome measures, validation plan, statistics plan, sensitivity analyses, and reproducibility framework. It contains NO simulated results, because none exist yet - no COMSOL simulation has been run in this project.
Sheet 6 (Simulation Matrix) defines 24 planned experiments: 6 clinical groups (Sheet 3) x 4 gravity scenarios (Sheet 2). Every row's Status is 'Planned'. Sheet 20 (Experiment Execution Tracker) confirms this programmatically: every experiment shows Planned=Yes, Started=No, Completed=No, Validated=No.
Sheet 12 (Expected Physiological Changes) deliberately contains NO quantitative predictions - only qualitative, literature-grounded directional reasoning (e.g. 'reduced preload is expected under reduced gravity, per general spaceflight physiology literature'), and is explicit where the literature itself does not support committing to a predicted direction (e.g. stroke volume and cardiac output changes are reported as mixed/timescale-dependent in the spaceflight literature, so no single direction is predicted here).
Consistency with the three prior workbooks in this project:
- Gravity constants (Sheet 2) are identical to Digital_Twin_Construction_Protocol...xlsx Sheet 10, Simulation_Input_Parameter_Workbook.xlsx Sheet 6, and COMSOL_Model_Implementation_Workbook.xlsx Sheet 10.
- Experimental Groups (Sheet 3) map directly to the actual diagnosis categories and sample sizes documented in Master_Analytical_Cohort_Digital_Twin.xlsx (e.g. ACDC's 5 groups of 20, Sunnybrook's N=9/HYP=12/HF=12/HF-I=12).
- Independent Variables (Sheet 4) and Sensitivity Analysis Plan (Sheet 10) reference the exact literature ranges documented in Simulation_Input_Parameter_Workbook.xlsx, not new or re-derived numbers.
Cohort basis: ACDC (100) + Sunnybrook (45) + CAMUS (500) = 645 subjects. This workbook contains no patient-level data and no simulation output data of any kind.