## Implementation Workflow
Step ID | Implementation Stage | Description | Input | Output | Software | Status | Notes
IMP-01 | Import Imaging Data | Load raw NIfTI (ACDC) / DICOM (Sunnybrook) / raw-mhd or HDF5 (CAMUS) imaging series into the processing environment. | Raw dataset files (ACDC available; Sunnybrook/CAMUS access-gated or not yet downloaded per prior workbooks) | In-memory or on-disk image arrays with header metadata | Python (nibabel, pydicom, SimpleITK) | Planned | Blocked on obtaining Sunnybrook/CAMUS raw files (see Master_Analytical_Cohort_Digital_Twin.xlsx provenance notes).
IMP-02 | Import Segmentation | Load expert ground-truth segmentation masks/contours corresponding to each imported imaging series. | Dataset segmentation masks (ACDC, CAMUS) / contour files (Sunnybrook) | In-memory label arrays / contour point sets | Python (nibabel, SimpleITK, numpy) | Planned | Same blocker as IMP-01 for Sunnybrook/CAMUS.
IMP-03 | Surface Reconstruction | Extract triangulated surfaces (LV/RV/myocardium or LV/LA) from segmentation masks. | Segmentation masks/contours (IMP-02 output) | Raw STL surface mesh per structure per phase (ED, ES) | VTK (marching cubes) / 3D Slicer | Planned | See Sheet 4 for the detailed sub-steps.
IMP-04 | Geometry Cleaning | Repair holes, remove self-intersections, and correct non-manifold topology in the raw surface mesh. | Raw STL surface (IMP-03 output) | Watertight, manifold surface mesh | VTK / MeshLab / Meshmixer | Planned | See Sheet 4.
IMP-05 | Mesh Generation | Generate the volumetric tetrahedral finite-element mesh from the cleaned surface. | Cleaned surface mesh (IMP-04 output) | Volumetric tetrahedral mesh | COMSOL Multiphysics built-in mesher, or Gmsh | Planned | See Sheet 5 and Simulation_Input_Parameter_Workbook.xlsx for target mesh quality parameters.
IMP-06 | Material Assignment | Assign passive/active myocardial and blood material properties to mesh regions. | Volumetric mesh (IMP-05) + Simulation_Input_Parameter_Workbook.xlsx Sheets 2-3 | Material-tagged mesh regions in COMSOL | COMSOL Multiphysics (Solid Mechanics module) | Planned | See Sheet 7.
IMP-07 | Fiber Assignment | Apply the rule-based fiber helix/sheet angle field across the myocardial wall. | Volumetric mesh (IMP-05) + Simulation_Input_Parameter_Workbook.xlsx Sheet 4 | Fiber orientation vector field on mesh | Custom rule-based script (Bayer et al. 2012 method) + COMSOL material orientation import | Planned | See Sheet 8.
IMP-08 | Boundary Condition Assignment | Apply pressure loading, valve conditions, base constraints, and pericardial restraint to the model. | Meshed, material-assigned geometry + Simulation_Input_Parameter_Workbook.xlsx Sheet 5 | Fully constrained COMSOL model boundaries | COMSOL Multiphysics | Planned | See Sheet 9.
IMP-09 | Physics Setup | Configure the relevant COMSOL physics interfaces (Solid Mechanics, and optionally Laminar Flow / FSI). | Meshed, material- and boundary-condition-assigned model | Configured COMSOL physics interfaces | COMSOL Multiphysics | Planned | See Sheet 6.
IMP-10 | Solver Setup | Configure solver type, time stepping, tolerances, and iteration limits. | Configured physics interfaces + Simulation_Input_Parameter_Workbook.xlsx Sheet 7 | Configured COMSOL study/solver sequence | COMSOL Multiphysics | Planned | See Sheet 11.
IMP-11 | Gravity Configuration | Apply the gravitational body-force load for each of the four scenarios (Earth/Mars/Moon/Microgravity). | Configured model + Simulation_Input_Parameter_Workbook.xlsx Sheet 6 | Gravity-scenario-specific model variants | COMSOL Multiphysics (body force / gravity feature) | Planned | See Sheet 10. Gravity values themselves are fully specified (exact physical constants); only their application inside a COMSOL model is pending.
IMP-12 | Simulation Execution | Run the configured solver for each scenario. | Fully configured COMSOL model (all prior steps complete) | Raw simulation result files (.mph with solution data) | COMSOL Multiphysics | Planned | NO simulation has been executed in this project. This step cannot begin until IMP-01 through IMP-11 are complete.
IMP-13 | Post-processing | Generate derived visualizations and summary curves from raw simulation output. | Raw simulation results (IMP-12 output) | Pressure/velocity/stress/strain maps, PV loops, time curves | COMSOL post-processing, ParaView | Planned | See Sheet 12. Cannot begin until IMP-12 produces results.
IMP-14 | Validation | Compare simulation outputs against dataset-derived and literature validation targets. | Post-processed results (IMP-13) + Simulation_Input_Parameter_Workbook.xlsx Sheet 9 (Validation Targets) | Validation report | Python (numpy/scipy) or COMSOL post-processing | Planned | See Sheet 13. Cannot begin until IMP-13 produces results.
IMP-15 | Export | Export final model files, meshes, scripts, figures, and validated results for archival and manuscript use. | Validated results (IMP-14) + all intermediate pipeline artifacts | Archived deliverables per Sheet 19 (Repository Deliverables) | COMSOL Multiphysics, Python, file system | Planned | Cannot begin until IMP-14 is complete.

## Software Environment
Software | Purpose | Version | License | Status | Notes
COMSOL Multiphysics | Primary FE simulation platform (meshing, physics, solver, post-processing) | To be recorded at implementation | Commercial (institutional/departmental license required - not yet confirmed for this project) | Planned | No COMSOL model has been created yet.
Python | Data harmonization, preprocessing, scripting, and (optionally) COMSOL LiveLink automation | 3.x - To be recorded at implementation | Open source (PSF License) | Planned (partially in use for prior cohort-harmonization workbooks) | Used already for the three prior cohort workbooks; not yet used for any imaging/meshing step in this implementation.
MATLAB (if applicable) | Optional auxiliary analysis or COMSOL LiveLink for MATLAB automation | To be recorded at implementation | Commercial (not yet confirmed for this project) | Planned (optional) | Only needed if LiveLink-for-MATLAB automation is chosen over the Python route.
3D Slicer | Interactive segmentation review and surface extraction | To be recorded at implementation | Open source (BSD-style) | Planned | Not yet installed/used in this project.
ParaView | Post-processing visualization of meshes and simulation results | To be recorded at implementation | Open source (BSD-style) | Planned | Not yet installed/used in this project.
VTK | Surface extraction (marching cubes), mesh manipulation | To be recorded at implementation | Open source (BSD-style) | Planned | Not yet installed/used in this project.
SimpleITK | Medical image I/O, filtering, resampling, registration | To be recorded at implementation | Open source (Apache 2.0) | Planned | Not yet installed/used in this project.
NumPy | Array operations underlying all Python image/data processing | To be recorded at implementation | Open source (BSD-style) | Planned (in use for prior cohort-harmonization workbooks) | Already a dependency of the existing openpyxl-based cohort scripts.
SciPy | Numerical/scientific computing utilities (e.g. interpolation, optimization for calibration) | To be recorded at implementation | Open source (BSD-style) | Planned | Not yet used in this project.
MeshLab | Mesh repair, smoothing, and topology correction | To be recorded at implementation | Open source (GPL) | Planned | Not yet installed/used in this project.
Gmsh | Alternative open-source volumetric mesh generator (if not using COMSOL's built-in mesher) | To be recorded at implementation | Open source (GPL) | Planned (optional/alternative to COMSOL native meshing) | Not yet installed/used in this project.

## Data Import Pipeline
Step | Input Format | Output Format | Tool | Validation
DICOM | DICOM (.dcm) | In-memory pixel array + header metadata | pydicom (Python) | Header sanity check: PixelSpacing/SliceThickness/dimensions match documented Sunnybrook acquisition specs
NIfTI | NIfTI (.nii.gz) | In-memory voxel array + affine/header metadata | nibabel (Python) | Header sanity check: voxel spacing/dimensions match documented ACDC/CAMUS specs
Segmentation Masks | NIfTI/DICOM label volumes or contour point text files | In-memory binary/multi-label arrays or point sets | Python (numpy, SimpleITK) | Label value set matches documented dataset convention (e.g. ACDC: 1=RV, 2=MYO, 3=LV)
STL | Surface mesh from marching cubes | STL (.stl) triangulated surface file | VTK / 3D Slicer | Re-import and vertex/face count match; watertight check
VTK | STL or other mesh formats | VTK (.vtu/.vtk) mesh with associated field data | VTK / meshio (Python) | Format round-trip check (export then re-import, compare geometry)
COMSOL Geometry | STL surface or external volumetric mesh | COMSOL-native geometry/mesh object (within .mph file) | COMSOL Multiphysics (Import > Geometry, or LiveLink) | COMSOL import log review; element count/quality report from COMSOL

## Geometry Construction
Step | Method | Software | Input | Output | Quality Metric
Surface Extraction | Marching cubes on binary/multi-label segmentation volume | VTK | Segmentation mask (per structure, per phase) | Raw triangulated surface | Triangle count; watertight check (0 open edges)
Hole Filling | Automatic hole-filling on identified boundary loops | VTK / MeshLab | Raw triangulated surface (with holes, if any) | Hole-free surface | Number of remaining open boundary edges (target: 0)
Smoothing | Laplacian or Taubin smoothing | VTK / MeshLab | Hole-filled surface | Smoothed surface | Volume preservation: pre/post-smoothing volume within ~1-2% (per Digital Twin Construction Protocol workbook, Sheet 3)
Topology Correction | Non-manifold edge/vertex removal; self-intersection resolution | VTK / MeshLab / Meshmixer | Smoothed surface | Manifold, self-intersection-free surface | Manifoldness check; Euler characteristic consistent with expected topology (sphere-like cavity)
Surface Validation | Visual inspection + automated mesh-quality metric check | VTK / ParaView / 3D Slicer | Corrected surface | Validated surface ready for STL export | Surface quality metric (per Digital Twin Construction Protocol workbook, Sheet 5, >= 0.3 on 0-1 scale)
STL Export | Direct file export | VTK / 3D Slicer / MeshLab | Validated surface | Per-structure, per-phase STL file (e.g. patientID_LV_ED.stl) | File integrity check (re-import and vertex/face count match)

## Mesh Implementation
Mesh Stage | Method | Parameter | Quality Metric | Validation
Surface Mesh | Triangulated surface from Geometry Construction (Sheet 4) | Target triangle edge length: TBD (mesh independence study pending) | Surface quality >= 0.3 (0-1 scale) | COMSOL/VTK mesh quality report
Volume Mesh | Tetrahedral volumetric meshing | Physics-controlled mesh size 'Normal' to 'Fine' as a starting point (per Simulation_Input_Parameter_Workbook.xlsx Sheet mesh guidance in the prior protocol workbook) | Volume quality >= 0.1 minimum element quality | COMSOL mesh statistics report
Adaptive Refinement | Local refinement near high-curvature/high-gradient regions (e.g. apex, valve annuli) | Enabled for structural mechanics regions of interest; exact refinement criteria: TBD | N/A - qualitative refinement strategy, not a single scalar | Visual/quantitative comparison of refined vs. unrefined region element density
Mesh Independence | Successive mesh refinement with key-output-variable convergence tracking | Convergence criterion: < 5% change in key output (e.g. peak wall stress) between successive refinement levels | Relative change in key output variable | Formal mesh independence study - not yet performed (no mesh has been generated)
Aspect Ratio | Element edge-length ratio check | Target <= 5:1; upper tolerance 10:1 before re-meshing | Ratio of longest to shortest element edge | COMSOL mesh statistics report
Jacobian | Element distortion check | Target >= 0.3 (positive, well away from 0=degenerate) | Ratio of min to max Jacobian determinant | COMSOL mesh quality report
Skewness | Element shape deviation check | Target <= 0.6; upper tolerance 0.8 | Deviation from ideal (equilateral) element shape | COMSOL / standard FE meshing guideline

## Physics Interfaces
Physics Interface | COMSOL Module | Purpose | Input Parameters | Output Variables | Future Work
Solid Mechanics | COMSOL Structural Mechanics Module | Model myocardial wall deformation under pressure loading and gravity body force | Material properties (Simulation_Input_Parameter_Workbook.xlsx Sheets 2-3), fiber orientation (Sheet 4), boundary conditions (Sheet 5), gravity load (Sheet 6) | Displacement, stress, strain fields | No - core interface
Laminar Flow | COMSOL CFD Module | Model intracavitary blood flow (optional, for CFD/FSI scenarios) | Blood density/viscosity (Simulation_Input_Parameter_Workbook.xlsx Sheet 1-2), cavity geometry, inlet/outlet boundary conditions | Velocity, pressure fields; wall shear stress | No - core interface
Fluid-Structure Interaction | COMSOL Structural Mechanics + CFD Modules (coupled) | Couple wall deformation with intracavitary flow (optional, future work) | Combined Solid Mechanics + Laminar Flow interface setup | Coupled displacement/stress/strain + velocity/pressure fields | Yes - optional/future
Moving Mesh (if planned) | COMSOL Deformed Geometry / Moving Mesh interface | Track the fluid domain's deformation as the myocardial wall moves (required for FSI, optional otherwise) | Solid Mechanics displacement field | Updated fluid domain mesh at each time step | Yes - optional/future
Global ODEs/DAEs (if planned) | COMSOL Mathematics > ODE and DAE Interfaces | Optional 0D lumped-parameter circulation model (e.g. simplified valve or afterload model) coupled to the 3D domain | Lumped-parameter circulation model equations (not yet defined) | Time-varying pressure/flow boundary values for the 3D model | Yes - optional/future

## Material Assignment
Region | Material Model | Parameter Source | Assignment Method | Status
LV Wall | Holzapfel-Ogden or Guccione (anisotropic hyperelastic) - selection pending (see Simulation_Input_Parameter_Workbook.xlsx Sheet 3) | Simulation_Input_Parameter_Workbook.xlsx Sheets 2-3 | COMSOL user-defined material with anisotropic hyperelastic strain energy function; fiber directions imported from Fiber Orientation Implementation (Sheet 8) | Planned
RV Wall (where applicable) | Same constitutive model family as LV Wall (ACDC-based scenarios only, since RV geometry is available only from ACDC) | Simulation_Input_Parameter_Workbook.xlsx Sheets 2-3 (RV-specific parameter values not separately published - LV parameters used as a starting approximation, to be flagged explicitly in any manuscript use) | Same as LV Wall | Planned
Blood | Newtonian incompressible fluid | Simulation_Input_Parameter_Workbook.xlsx Sheet 1-2 (density ~1050-1060 kg/m^3, viscosity ~0.0035-0.004 Pa.s) | COMSOL built-in fluid material (Laminar Flow interface), if CFD/FSI scenarios are pursued | Planned (only needed for CFD/FSI scenarios)
Valves (if modeled) | Not currently modeled as deformable structures - idealized boundary condition instead (see Boundary Condition Implementation, Sheet 9) | N/A - not applicable given current idealized treatment | N/A - not applicable | Planned (future work if deformable valve modeling is added to project scope)

## Fiber Orientation Impl
Step | Method | Source | Software | Status
Rule-based assignment | Laplace-Dirichlet Rule-Based method (Bayer, Blake, Plank & Trayanova 2012): solve Laplace's equation between endo/epi surfaces, interpolate helix angle transmurally | Literature-derived algorithm (Simulation_Input_Parameter_Workbook.xlsx Sheet 4) | Custom Python/VTK implementation, or COMSOL PDE interface for the Laplace solve | Planned - recommended default method given no DT-MRI data exists for ACDC, Sunnybrook, or CAMUS
Atlas mapping | Registration of subject geometry to a published DT-MRI cardiac atlas, then transfer of the atlas fiber field | Atlas-derived (specific atlas not yet selected) | Registration toolkit (e.g. SimpleITK/ANTs) + custom field-transfer script | Planned (alternative method, not yet chosen over rule-based)
Manual definition (if applicable) | Direct manual specification of fiber angles for simplified/idealized test geometries only | User-defined simulation assumption | COMSOL material orientation input (manual entry) | Planned (reserved for simplified verification/test cases only, not the primary subject-derived geometry pipeline)

## Boundary Condition Impl
Boundary | Type | Value Source | Application Method | Status
Base constraint | Displacement constraint at basal plane/valve annulus | User-defined simulation assumption (Simulation_Input_Parameter_Workbook.xlsx Sheet 5) | COMSOL Fixed Constraint or Spring Foundation boundary condition applied to the basal cut surface | Planned
Mitral inlet | Idealized open/closed gate | User-defined simulation assumption (Simulation_Input_Parameter_Workbook.xlsx Sheet 5) | COMSOL boundary condition switching (time-dependent enable/disable) or pressure-controlled valve logic | Planned
Aortic outlet | Pressure or flow outlet condition (CFD/FSI scenarios) | User-defined simulation assumption (Simulation_Input_Parameter_Workbook.xlsx Sheet 5 - value TBD) | COMSOL Pressure or Outlet boundary condition (Laminar Flow interface) | Planned (CFD/FSI scenarios only)
Initial pressure | Initial condition for time-dependent solve | Literature-derived ED pressure range (~8-12 mmHg LV; Simulation_Input_Parameter_Workbook.xlsx Sheet 5) | COMSOL Initial Values node | Planned
Initial velocity | Initial condition for time-dependent solve (CFD/FSI scenarios) | User-defined simulation assumption: zero initial velocity | COMSOL Initial Values node (Laminar Flow interface) | Planned (CFD/FSI scenarios only)
Pericardial support | Contact/normal-restraint boundary condition on epicardial surface | To be calibrated - no single consensus literature value found (Simulation_Input_Parameter_Workbook.xlsx Sheet 5) | COMSOL Spring Foundation (normal direction) on the epicardial boundary | Planned

## Gravity Implementation
Scenario | Gravity | Vector | COMSOL Feature | Status | Notes
Earth | 1 g | (0, -9.80665, 0) | COMSOL Global Forces / Gravity feature under Solid Mechanics (body force load) | Planned | Value fully specified (exact SI standard gravity); not yet applied inside an actual COMSOL model.
Mars | 0.38 g | (0, -3.71, 0) | Same COMSOL Gravity feature, alternate scenario configuration | Planned | Value fully specified (published Mars surface gravity); not yet applied.
Moon (optional) | 0.16 g | (0, -1.62, 0) | Same COMSOL Gravity feature, alternate scenario configuration | Planned | Value fully specified (published lunar surface gravity); not yet applied.
Microgravity | 0 g | (0, 0, 0) | Same COMSOL Gravity feature, alternate scenario configuration (or feature disabled entirely) | Planned | Idealized zero-gravity condition; not yet applied.

## Solver Implementation
Setting | Selected Option | Justification | Status
Time-dependent solver | COMSOL Time Dependent study step, implicit variable-step scheme (generalized-alpha or BDF) | Required for full cardiac cycle simulation through ED-ES-ED; implicit schemes are more stable for stiff nonlinear structural problems | Planned
Stationary solver | COMSOL Stationary study step, for single-phase (e.g. peak-systole-only) simplified scenarios | Useful for initial model verification before committing to full time-dependent runs | Planned
Newton iteration | Damped Newton (COMSOL default for nonlinear structural mechanics) | Standard choice for large-deformation hyperelastic problems | Planned
Time step | To be determined | Depends on final Heart Rate value (currently NA per-subject, per Master Analytical Cohort workbook) and mesh/solver convergence behavior; a conservative starting estimate is cardiac-cycle-duration/100-1000, to be refined by a convergence study | Planned
Relative tolerance | To be determined | COMSOL default relative tolerance is 1e-3; final value pending a formal convergence study (not yet performed) | Planned
Absolute tolerance | To be determined | Problem-scale-dependent (depends on final units and expected magnitude of solution variables); to be set once a specific scenario's expected value ranges are established | Planned
Maximum iterations | COMSOL default (25 for the nonlinear solver) as a starting point | Standard starting point; to be increased if convergence is not reached within this budget during initial test runs | Planned

## Post-processing Pipeline
Output | Software | Visualization Method | Export Format
Pressure maps | COMSOL post-processing, or ParaView (if exported) | Surface/volume color plot over the cardiac cycle | PNG/VTU + animation (AVI/MP4)
Velocity vectors | COMSOL post-processing, or ParaView | Vector field plot (arrow/glyph plot) on a cavity slice | PNG/VTU + animation
Streamlines | COMSOL post-processing, or ParaView | Streamline plot through the cavity | PNG/VTU + animation
Wall stress | COMSOL post-processing | Surface color plot (Von Mises or principal stress) on the myocardial wall | PNG/VTU + animation
Wall strain | COMSOL post-processing | Surface color plot (principal strain) on the myocardial wall | PNG/VTU + animation
PV loops | COMSOL Global Evaluation + Python/matplotlib for final figure formatting | 2D line plot: cavity volume (x) vs. cavity pressure (y) over one cardiac cycle | PNG/SVG (vector) + underlying data as CSV
Time curves | COMSOL Global Evaluation + Python/matplotlib | 2D line plot: selected output variable vs. time | PNG/SVG + underlying data as CSV
Animations | COMSOL Animation export, or ParaView | Time-sequenced render of deformation/field results | AVI/MP4/GIF

## Validation Workflow
Validation Step | Comparator | Acceptance Criterion | Evidence | Status
Geometry validation | Mesh-derived cavity volume vs. dataset-derived LV_EDV/ESV (ACDC, resolved) | <= 5-10% volume difference (literature-derived tolerance, Simulation_Input_Parameter_Workbook.xlsx Sheet 9) | Not yet available - no geometry has been reconstructed | Planned
Mesh convergence | Key output variable (e.g. peak wall stress) across successive mesh refinement levels | < 5% change between the two finest refinement levels tested | Not yet available - no mesh has been generated | Planned
Numerical convergence | Solver residual norm and output-variable stability across solver tolerance settings | Residual below configured tolerance (Sheet 11); output variable stable to within defined tolerance across tolerance settings | Not yet available - no simulation has been run | Planned
EF comparison | Simulation-derived EF vs. dataset-derived LV_EF_percent (ACDC, resolved) | Within 5 percentage points (Simulation_Input_Parameter_Workbook.xlsx Sheet 9) | Not yet available - no simulation has been run | Planned
Volume comparison | Simulation-derived cavity volume vs. dataset-derived LV_EDV/ESV | Within 5-10% (Simulation_Input_Parameter_Workbook.xlsx Sheet 9) | Not yet available - no simulation has been run | Planned
Sensitivity analysis | Parametric sweep of key literature-derived parameters (e.g. passive stiffness, pressure) with output response tracked | Study-dependent; to be defined once a specific output variable and acceptable variance are chosen | Not yet available - no simulation has been run | Planned

## File Organization
Folder | Contents | Purpose | Version Control
Raw_Data | Original downloaded dataset files (ACDC NIfTI; Sunnybrook DICOM/contours once obtained; CAMUS raw-mhd/HDF5 once obtained) - read-only | Preserve an untouched copy of source data for reproducibility | Not version-controlled directly (large binary files); tracked via a manifest file with checksums instead
Processed_Data | Preprocessed image arrays, resampled volumes, extracted label masks | Intermediate pipeline outputs, regenerable from Raw_Data + Scripts | Not version-controlled directly (regenerable); tracked via processing-script version instead
Mesh | STL surfaces, volumetric meshes (per subject, per structure, per phase) | Geometry/meshing pipeline outputs | Not version-controlled directly (large binary files); archived alongside a manifest
COMSOL | .mph model files, one per scenario (per Digital Twin Construction Protocol workbook, Sheet 11 scenario list) | COMSOL model archive | Version-controlled via file naming convention + changelog (COMSOL .mph files are binary and not git-diff-friendly)
Scripts | Python (and, if used, MATLAB) scripts for every pipeline stage: cohort harmonization (existing), preprocessing, meshing, fiber generation, post-processing analysis | Reproducible processing code | Git version control (recommended primary VC target for this project)
Results | Raw and processed simulation output data (CSV time curves, exported field data) | Quantitative simulation outputs | Git version control for small CSV/summary files; large field-data files tracked via manifest
Figures | Final manuscript-ready figures (per Digital Twin Construction Protocol workbook, Sheet 19 Manuscript Figure Planning) | Publication deliverables | Git version control
Supplementary | All workbook files from this project (cohort workbooks, protocol workbook, parameter workbook, this implementation workbook) plus any supplementary tables/figures | Supplementary Materials package for manuscript submission | Git version control

## Computational Resources
Resource | Minimum Requirement | Recommended Requirement | Notes
CPU | Multi-core, >= 4 cores (general workstation minimum) | >= 8-16 cores (per COMSOL's general system requirement guidance for 3D structural/CFD problems) | Final requirement depends on mesh size, which is not yet determined (mesh independence study pending)
RAM | >= 16 GB | >= 32-64 GB (for finer meshes and larger 3D biomedical models, per COMSOL general guidance) | Direct solvers (MUMPS/PARDISO) are memory-intensive; final requirement depends on final mesh element count
GPU (if used) | Not required for COMSOL structural solvers (primarily CPU-based) | Optional - may benefit CFD scenario solvers depending on final solver choice, and is recommended for interactive ParaView visualization of large results | To be confirmed against final COMSOL module/solver selection (Sheet 6, 11)
Storage | >= 100 GB free (accounting for CAMUS HDF5 mirror alone being ~25.5 GB per its own documentation, plus mesh/result files) | >= 500 GB - 1 TB (for multiple scenario runs, mesh refinement studies, and archived results) | Final requirement depends on number of scenarios and mesh refinement levels actually run
Operating System | Windows, Linux, or macOS (per COMSOL Multiphysics system requirements) | Same, 64-bit, current supported OS version at time of installation | No specific OS has been fixed for this project yet

## Risk and Mitigation
Risk | Likelihood | Impact | Mitigation Strategy | Status
Mesh failure | Medium | High (blocks all downstream simulation steps) | Apply topology correction (Sheet 4) before meshing; use COMSOL/VTK mesh diagnostics to catch failures early; iterate smoothing parameters if repair fails | Planned (mitigation strategy defined, not yet tested against a real mesh)
Solver divergence | Medium | High (prevents obtaining any simulation result for a scenario) | Use load ramping/continuation methods; start from a converged lower-load solution; tune Newton damping and tolerance (Sheet 11); verify mesh quality first | Planned (mitigation strategy defined, not yet tested)
Poor image quality | Medium (CAMUS officially documents 19% of its images as poor quality) | Medium (affects reliability of geometry derived from affected subjects/frames) | Flag and, where feasible, exclude or separately report on subjects/frames with documented poor image quality; do not treat all segmentations as equally reliable in downstream analysis | Planned (known risk, documented; mitigation not yet applied since no geometry pipeline has run)
Missing parameters | High (confirmed - see Simulation_Input_Parameter_Workbook.xlsx for numerous 'To be calibrated'/blank cells) | Medium-High (blocks or weakens specific physics/scenarios, e.g. pericardial constraint stiffness, heart rate) | Use documented literature ranges where available; explicitly flag any assumption-based value in manuscript reporting; pursue calibration studies for genuinely unknown parameters before final production runs | Planned
Numerical instability | Medium | High (produces unreliable or non-physical results if undetected) | Perform a time-step convergence study; use implicit time-stepping (COMSOL default for structural mechanics); monitor solver residuals during runs | Planned (mitigation strategy defined, not yet tested)

## Quality Assurance
Check | Method | Frequency | Evidence | Status
Geometry inspection | Visual review (ParaView/3D Slicer) + automated watertight/manifold check | After every Geometry Construction run (Sheet 4), per subject/structure/phase | Not yet available - no geometry has been constructed | Planned
Mesh inspection | COMSOL/VTK mesh quality report (aspect ratio, skewness, Jacobian) reviewed against targets in Sheet 5 | After every Mesh Implementation run (Sheet 5) | Not yet available - no mesh has been generated | Planned
Parameter verification | Cross-check every material/boundary/solver parameter entered into COMSOL against Simulation_Input_Parameter_Workbook.xlsx before each run | Before every simulation run | Not yet available - no simulation has been run | Planned
Unit consistency | Explicit unit-conversion review (e.g. mmHg-to-Pa, kPa-to-Pa) for every parameter entering COMSOL, since COMSOL's internal unit system must match the source literature/dataset units | Before every simulation run | Not yet available - no simulation has been run | Planned
Result sanity check | Compare simulation output order-of-magnitude and sign against physiological expectation (e.g. positive systolic pressure, EF between 0-100%) before formal validation (Sheet 13) | Immediately after every simulation run, before formal validation | Not yet available - no simulation has been run | Planned

## Manuscript Mapping
Workbook Section | Corresponding Manuscript Section | Planned Figure/Table | Supplementary Material
Sheet 1 Implementation Workflow | Methods - Digital Twin Construction Pipeline | Figure: pipeline workflow diagram | Table: full Implementation Workflow (this sheet)
Sheet 4 Geometry Construction / Sheet 5 Mesh Implementation | Methods - Geometry and Mesh Generation | Figure: example reconstructed geometry and mesh (once available) | Table: mesh quality metrics per subject/scenario (once available)
Sheet 6 Physics Interfaces / Sheet 7 Material Assignment / Sheet 8 Fiber Orientation Implementation | Methods - Constitutive Modeling and Physics Setup | Figure: fiber orientation field visualization (once available) | Table: Simulation_Input_Parameter_Workbook.xlsx Sheets 2-4 (material/constitutive/fiber parameters)
Sheet 9 Boundary Condition Implementation / Sheet 10 Gravity Implementation | Methods - Boundary Conditions and Gravity Scenarios | Figure: gravity scenario comparison diagram | Table: Simulation_Input_Parameter_Workbook.xlsx Sheets 5-6 (boundary condition and gravity matrix)
Sheet 11 Solver Implementation | Methods - Numerical Solution Procedure | N/A - typically described in text, not a standalone figure | Table: solver settings and justification (this sheet)
Sheet 12 Post-processing Pipeline / Sheet 13 Validation Workflow | Results - Simulation Outputs and Validation | Figures: pressure/velocity/stress/strain maps, PV loops, time curves (all pending actual simulation runs) | Table: validation metrics and acceptance criteria (this sheet + Simulation_Input_Parameter_Workbook.xlsx Sheet 9)
Sheet 16 Risk and Mitigation / Sheet 17 Quality Assurance | Methods/Discussion - Limitations and Quality Control | N/A - typically described in text | Table: risk assessment and QA checklist (these sheets)
Sheet 19 Repository Deliverables | Data and Code Availability statement | N/A | Direct link to public repository/archive once created (not yet available)

## Repository Deliverables
File | Description | Format | Public Release Status
COMSOL model | .mph file(s), one per simulation scenario | .mph | Planned - not yet created
Mesh files | Volumetric mesh per subject/scenario | .mphtxt / .vtu / STL surfaces | Planned - not yet created
Python scripts | Cohort harmonization (existing), preprocessing, meshing, fiber generation, post-processing analysis scripts | .py | Partially available - cohort harmonization scripts exist; other stages' scripts not yet written since those pipeline stages have not started
Parameter tables | Simulation_Input_Parameter_Workbook.xlsx and this workbook's material/boundary/solver sheets | .xlsx | Available now
Figures | Manuscript figures per Sheet 18 mapping | .png / .svg | Planned - most figures blocked pending pipeline execution (see Digital Twin Construction Protocol workbook, Sheet 19)
README | Repository-level README describing project structure, dependencies, and how to reproduce each pipeline stage | .md | Planned - not yet written (this workbook and its companions could form the basis of its content)

## Implementation Progress Tracker
Task | Planned | Started | Completed | Evidence | Notes
Import Imaging Data | Yes | No | No | N/A - not started | Blocked on Sunnybrook/CAMUS raw file access.
Import Segmentation | Yes | No | No | N/A - not started | Same blocker as above.
Surface Reconstruction | Yes | No | No | N/A - not started
Geometry Cleaning | Yes | No | No | N/A - not started
Mesh Generation | Yes | No | No | N/A - not started
Material Assignment | Yes | No | No | N/A - not started | Parameter values largely specified in Simulation_Input_Parameter_Workbook.xlsx; application to an actual mesh not started.
Fiber Assignment | Yes | No | No | N/A - not started
Boundary Condition Assignment | Yes | No | No | N/A - not started
Physics Setup | Yes | No | No | N/A - not started
Solver Setup | Yes | No | No | N/A - not started
Gravity Configuration | Yes | No | No | N/A - not started | Gravity scenario values are fully specified (Sheet 10); application inside COMSOL not started.
Simulation Execution | Yes | No | No | N/A - not started | Cannot start until all preceding tasks are complete.
Post-processing | Yes | No | No | N/A - not started
Validation | Yes | No | No | N/A - not started
Export | Yes | No | No | N/A - not started

## README
COMSOL Model Implementation Workbook
This is an ENGINEERING IMPLEMENTATION GUIDE, not a results report. It documents exactly how the previously specified Digital Twin Construction Protocol and Simulation Input Parameter Workbook would be executed in COMSOL Multiphysics - every step, tool, physics interface, solver setting, and quality check - without claiming any of it has actually been run.
STATUS, STATED PLAINLY: as of this workbook, NO imaging data has been imported into a modeling pipeline, NO geometry has been reconstructed, NO mesh has been generated, and NO COMSOL simulation has been executed for this project. Every Status field in every sheet reflects this honestly - 'Planned' is used throughout rather than 'Complete', consistent with the instruction not to fabricate implementation status.
Software versions (Sheet 2) are recorded as 'To be recorded at implementation' rather than a specific version number, because no software has actually been run for this implementation yet - stating a specific COMSOL/Python/etc. version now would itself be a fabricated value.
Consistency with the prior two workbooks:
- Every material, fiber, boundary condition, and gravity value referenced here points back to Simulation_Input_Parameter_Workbook.xlsx rather than re-stating or re-deriving numbers - this workbook is about HOW those parameters would be applied inside COMSOL, not what their values are.
- The pipeline stage list (Sheet 1) matches the Digital Twin Construction Protocol workbook's Sheet 3/4 (Geometry Construction Pipeline / Image Processing Workflow) one-for-one, expanded into COMSOL-specific implementation detail.
- The four gravity scenarios (Sheet 10) are the same Earth/Mars/Moon/Microgravity values specified in both prior workbooks - values are exact physical constants, fully specified; only their application inside an actual COMSOL model is pending.
Cohort basis (unchanged from prior workbooks): ACDC (100) + Sunnybrook (45) + CAMUS (500) = 645 subjects, documented in Master_Analytical_Cohort_Digital_Twin.xlsx. This workbook contains no patient-level data.